## Timeline
JWST June 2021 Working Commissioning Timeline
Cooldown Profile: BPlot_All_metrics_LA13B_v5.5t18d-C_PH_V4_CC state4 at 82 days.xlsx
Changes 2020 | CAR # |  | CAR Title | MET Start |  | Duration |  | MET End
| 0 | 41 | Switch from External Power to Internal | -15 | min | 1 | min | -14 | min
| 40 | 41 | H0 | 0 | min | 0.12 | min | 0.12 | min
| 41 |  | EAP Ignition (H0 + 7.05s) | 0.1175 | min | 0.001 | min | 0.1185 | min
| 42 | 41 | Liftoff | 0.1216 | min | 0.5 | min | 0.6216 | min
| 734 | 41 | H1 (LV Acceleration Threshold Detection) | 2.3545 | min | 0.5 | min | 2.8545 | min
| 43 | 41 | EAP Separation (H1 + 0.78s) | 2.3675 | min | 0.1 | min | 2.4675 | min
| 891.01 |  | Alarm Limit Transition #1 (Prior to Fairing Separation) | 2.4675 | min | 1 | min | 3.4675 | min
| 44 | 41 | K1 (Fairing Jettison) | 3.4 | min | 0.1 | min | 3.5 | min
| 45 | 41 | Issue Discrete Cmd 1 (K1 + 27s) | 3.85 | min | 0.01 | min | 3.86 | min
| 46 | 41 | Issue Discrete Cmd 2 (K1 + 27.1s) | 3.85 | min | 0.016 | min | 3.866 | min
| 275 |  | Ascent SCS | 3.85 | min | 13.55 | min | 17.4 | min
| 128 | 275 | Turn ON S-band Xmtr 2 | 3.9167 | min | 0.1 | min | 4.0167 | min
| 129 | 275 | Turn ON all Catbed heaters | 3.9167 | min | 0.1 | min | 4.0167 | min
| 1 | 275 | H2 (End of main thrust phase of EPC) | 8.72 | min | 0.016 | min | 8.736 | min
| 735 | 275 | EPC Separation (H2 + 6s) | 7.82 | min | 0.016 | min | 7.836 | min
| 2 | 275 | K2 ESC-A Ignition | 8.89 | min | 0.16 | min | 9.05 | min
| 130 | 275 | Turn ON FSS-1, SIRU-1A, 2A | 17.3 | min | 0.1 | min | 17.4 | min
| 891.02 |  | Alarm Limit Transition #2 (Post ACS Turn ON) | 17.4 | min | 1 | min | 18.4 | min
| 263 | 275 | H3 ESC-A Shutdown | 24.97 | min | 0.01 | min | 24.98 | min
| 3 | 275 | H4.1 LV Separation | 27.1 | min | 0.01 | min | 27.11 | min
| 274 |  | Separation SCS | 30 | min | 20 | min | 50 | min
New CAR (6/9/2021 MOWG) | 927 |  | Establish Command and Control on TDRSS | 30 | min | 1 | min | 31 | min
| 336 | 274 | Power ON VDE-1 | 30.011 | min | 1 | min | 31.011 | min
| 4 | 274 | Prepare to damp rates via thrusters | 30.012 | min | 1 | min | 31.012 | min
| 131 | 274 | Damp Rates (Via Thrusters) - ACS to Sun/Rate control | 30.15 | min | 2.3 | min | 32.45 | min
| 5 | 274 | Solar Array Deployment | 31 | min | 2 | min | 33 | min
| 682 | 274 | Release SC LRM GRP-02A/B, Solar Array Release SOLAR ARRAY -J3, Group = 2 | 31 | min | 2 | min | 33 | min
| 683 | 274 | Release SC LRM GRP-01A/B, Solar Array Release SOLAR ARRAY +J3, Group = 2 | 31 | min | 2 | min | 33 | min
| 874.01 |  | Transition to Malindi | 35 | min | 5 | min | 40 | min
| 6 | 274 | Start Attitude Control (RCS Sun point attitude) | 35.5 | min | 3.65 | min | 39.15 | min
| 27 |  | Configure for 4K downlink & 2K uplink | 40 | min | 7 | min | 47 | min
| 277 | 274 | Release OTE LRM GRP-10A/B, ADIR Part 1 Release | 45 | min | 0.1 | min | 45.1 | min
| 697 | 274 | Power ON Sunshield deployment and SC bus heaters | 45.1 | min | 2 | min | 47.1 | min
| 271 | 274 | Set TCS Relay Mode to Normal | 45.1 | min | 0.001 | min | 45.101 | min
| 272 | 274 | Set TCS HDE Mode to Operational | 45.1 | min | 0.001 | min | 45.101 | min
| 132 | 274 | Reconfigure Catbed Heaters | 45 | min | 0.1 | min | 45.1 | min
| 273 | 274 | Command SFSW to Cooldown Mode | 46 | min | 0.1 | min | 46.1 | min
| 10 | 274 | ADU Power ON & Configure to Operate Mode | 46.6 | min | 1 | min | 47.6 | min
| 11 |  | Initiate Ranging | 47 | min | 3 | min | 50 | min
| 276 | 274 | Turn ON WDE | 49 | min | 1 | min | 50 | min
| 30 | 274 | FSM Heater Activation | 56 | min | 0.1 | min | 56.1 | min
| 7 |  | Set SA Deployed Relay | 57 | min | 14 | min | 71 | min
| 379 | 7 | EPS Breakwire Override | 71 | min | 1 | min | 72 | min
| 896 |  | LV Sep Auto-Transition Timer | 72 | min | 10 | min | 82 | min
| 915 |  | Disable GAA Deadman SCS | 82 | min | 4 | min | 86 | min
| 902 |  | Separation Vector Uplink | 86 | min | 9 | min | 95 | min
| 13.1 |  | Star Tracker Power ON and Checkout | 95 | min | 5 | min | 100 | min
| 13.1 |  | Star Tracker Power ON and Checkout - Analysis | 100 | min | 120 | min | 220 | min
| 278 |  | Transition to DSN Canberra & Configure for 40K downlink | 114 | min | 8 | min | 122 | min
| 891.03 |  | Alarm Limit Transition #3 (At First DSN Contact) | 122 | min | 2 | min | 124 | min
| 23.1 |  | Update Command Lockout Timer (part 1) | 124 | min | 6 | min | 130 | min
| 854 |  | Ox Priming | 130 | min | 4 | min | 134 | min
| 842 |  | Ephemeris Table Check & Upload | 0.125 | day | 0.75 | hr | 0.15625 | day
| 13.2 |  | Star Tracker power ON & Checkout | 0.16319 | day | 0.083333 | hr | 0.16667 | day
| 891.04 |  | Alarm Limit Transition #4 (Post STA Checkout) | 0.17361 | day | 0.033333 | hr | 0.175 | day
| 15 |  | SCAT Test Burn (burn at L+7 hours) | 0.16667 | day | 4 | hr | 0.33333 | day
| 874.02 |  | Transition to Malindi & Configure for 4K downlink | 0.18 | day | 0.16667 | hr | 0.18694 | day
| 888 |  | Transition to DSN Madrid & Configure for 40K downlink | 0.25 | day | 0.16667 | hr | 0.25694 | day
| 16 |  | MCC-1a (burn at L+12.5h) | 0.35417 | day | 6.5 | hr | 0.625 | day
| 921 |  | Goldstone Ground Station Transition | 0.5625 | day | 0.1 | hr | 0.56667 | day
| 891.05 |  | Alarm Limit Transition #5 (Post MCC-1a) | 0.625 | day | 0.083333 | hr | 0.62847 | day
Updated duration (June CAWG) | 916.1 |  | Higher Bus Voltage for Deployments | 0.63547 | day | 0.67 | hr | 0.66 | day
| 17 |  | Targeted S-band PB of MCC-1a Data | 0.67 | day | 1 | hr | 0.71 | day
| 884 |  | Upload & Activate No-Burn Ephemeris and DSN Contact Schedule for GAA Active Pointing | 0.85 | day | 1.5 | hr | 0.9125 | day
| 856 |  | L&EO Clock Correlation | 0.9 | day | 0.2 | hr | 0.90833 | day
| 23.2 |  | Update Command Lockout Timer (part 2) | 0.91528 | day | 0.1 | hr | 0.91944 | day
| 335 | HEADER | BAGA Initial Move | 1 | day | 0.5 | hr | 1.0208 | day
| 72 | 335 | Power ON side A of DEU / DUC | 1 | day | 0.083333 | hr | 1.0035 | day
| 20 | 335 | Release SC LRM GRP-04A, HGA Boom HGA BOOM, Group = 1 | 1.0035 | day | 0.25 | hr | 1.0139 | day
| 284 |  | Gimbaled Antenna Assembly to Park Position | 1.0278 | day | 0.51 | hr | 1.049 | day
| 911.01 |  | Enable Sunline Rotation | 1.056 | day | 0.083333 | hr | 1.0594 | day
| 871 |  | Background Collection of OTE Temp & Strain gauge Tlm during Deployments | 1.0664 | day | 0.33333 | hr | 1.0803 | day
| 914 |  | SMSS In-board Hinge Motor Heating | 1.0872 | day | 28 | hr | 2.2539 | day
| 283 |  | Configure for MGA Operations | 1.0942 | day | 0.65 | hr | 1.1212 | day
| 31 |  | Comm Reconfiguration | 1.1282 | day | 0.11667 | hr | 1.1331 | day
| 891.06 |  | Alarm Limit Transition #6 (Post MGA Activation) | 1.1331 | day | 0.033333 | hr | 1.1344 | day
| 848 |  | Load IRSU CCH Parameter Set 2 | 1.1414 | day | 0.5 | hr | 1.1622 | day
| 879 |  | Check SS Motor Telemetry Prior to +5 deg pitch | 2.0833 | day | 0.41667 | hr | 2.1007 | day
| 912.01 |  | Disable Sunline Rotation | 2.1076 | day | 0.55 | hr | 2.1306 | day
| 922 |  | Enable Active Pointing of MGA | 2.2917 | day | 0.41667 | hr | 2.309 | day
Updated duration (June CAWG) | 21 |  | MCC-1b (burn at L+2.5d) | 2.3333 | day | 5.1 | hr | 2.55 | day
| 911.02 |  | Enable Sunline Rotation | 2.5486 | day | 0.41667 | hr | 2.566 | day
| 9.1 |  | ICDH Power On and Initialization (Part 1) | 2.7 | day | 1.12 | hr | 2.7467 | day
| 845.1 |  | OSS Engine Activation and Initialization (Part 1) | 2.7536 | day | 0.73 | hr | 2.784 | day
| 756.1 | NRS-33 | NIRSpec MSA Heater Activation during Cooldown | 2.791 | day | 0.65 | hr | 2.8181 | day
| 912.02 |  | Disable Sunline Rotation | 2.825 | day | 0.55 | hr | 2.8479 | day
| 253 |  | Perform attitude maneuver to +5 deg pitch attitude and hold during UPS FWD Deployment | 2.8549 | day | 0.24999 | hr | 2.8653 | day
| 538 |  | Set ACS Control System Gains for Deployments | 2.8722 | day | 0.2499 | hr | 2.8826 | day
| 687 | HEADER | Sunshield Fwd UPS Deployment Operations | 3 | day | 2.1 | hr | 3.0875 | day
| 285 | 687 | Release FWD UPS MRD and LRMs | 3 | day | 1.5333 | hr | 3.0639 | day
| 722 | 687 | Release SS MRD GRP-01A/B, Pre-FWD UPS PRE-UPS, FWD SC BUS -J3 SIDE OF +J3 PANEL, Group = 4 | 3 | day | 0.4 | hr | 3.0167 | day
| 721 | 687 | Release SS MRD GRP-02A/B, Pre-FWD UPS PRE-UPS, FWD OUTER 4-BAR -J3 SIDE oF 4-BAR PANEL, Group = 5 | 3.0236 | day | 0.4 | hr | 3.0403 | day
| 723 | 687 | Release SS LRM GRP-01A/B, Pre-FWD UPS LRM 1 & 2 (Fwd UPS Bipod Pair), +J1 / ±J2 UPS Bipod, Group = 2 | 3.0472 | day | 0.4 | hr | 3.0639 | day
| 24 | 687 | Sunshield FWD UPS Deployment | 3.0708 | day | 0.4 | hr | 3.0875 | day
| 891.07 |  | Alarm Limit Transition #7 (Post FWD UPS Deployment) | 3.0875 | day | 0.083333 | hr | 3.091 | day
| 255 |  | Perform attitude maneuver to -20 pitch for all remaining deployments | 3.0944 | day | 1.0001 | hr | 3.1361 | day
| 256 |  | DTA Deployment Motor Heating | 3.1569 | day | 21 | hr | 4.0319 | day
| 688 | HEADER | Sunshield AFT UPS Deployment Operations | 3.1569 | day | 2.67 | hr | 3.2682 | day
| 728 | 688 | Release AFT UPS MRD and LRMs | 3.1569 | day | 2.1 | hr | 3.2444 | day
| 555 | 688 | Release SS MRD GRP-03A/B. Pre-AFT UPS PRE-UPS, AFT SC BUS -J3 SIDE OF +J3 PANEL, Group = 4 | 3.1569 | day | 0.4 | hr | 3.1736 | day
| 556 | 688 | Release SS MRD GRP-04A/B. Pre-AFT UPS PRE-UPS, AFT FIXED 4-BAR -J3 SIDE OF 4-BAR PANEL, Group = 5 | 3.1806 | day | 0.4 | hr | 3.1972 | day
| 557 | 688 | Release SS MRD GRP-05A/B. Pre-AFT UPS PRE-UPS, OUTER 4-BAR -J3 SIDE OF 4-BAR PANEL, group = 5 | 3.2042 | day | 0.4 | hr | 3.2208 | day
| 558 | 688 | Release SS LRM GRP-02A/B. Pre-AFT UPS LRM 3 & 4, AFT -J1 / ±J2 UPS BIPOD, Group = 2 | 3.2278 | day | 0.4 | hr | 3.2444 | day
| 262 | 688 | Sunshield Aft UPS Deployment | 3.2514 | day | 0.4 | hr | 3.2681 | day
| 891.08 |  | Alarm Limit Transition #8 (Post AFT UPS Deployment) | 3.2681 | day | 0.083333 | hr | 3.2715 | day
| 911.03 |  | Enable Sunline Rotation | 3.2785 | day | 0.41667 | hr | 3.2958 | day
| 9.2 |  | ICDH power On and initialization (pt 2: Loads & Verification) | 3.5 | day | 1.88 | hr | 3.5783 | day
| 845.2 |  | OSS Engine Activation and Initialization (pt 2: Loads & Verification) | 3.5853 | day | 3.6 | hr | 3.7353 | day
| 912.03 |  | Disable Sunline Rotation | 3.9861 | day | 0.55 | hr | 4.009 | day
| 571 |  | DTA Deployment, DTA Sync move - set the motor phase | 4 | day | 0.083333 | hr | 4.0035 | day
| 337 | HEADER | Release MBA Spreader Bar to OTE LRMs | 4.0319 | day | 4.0332 | hr | 4.2 | day
| 559 | 337 | Release SS LRM GRP-03A/B, Pre-DTA Deploy +J2 MID-BOOM SPREADER BAR HOLD-DOWN LRM, Group = 1 | 4.0319 | day | 0.25003 | hr | 4.0424 | day
| 560 | 337 | Release SS LRM GRP-04A/B, Pre-DTA Deploy -J2 MID-BOOM SPREADER BAR HOLD-DOWN LRM, Group = 1 | 4.0493 | day | 0.25011 | hr | 4.0597 | day
| 539 | 337 | Release OTE LRM GRP-01A/B, DTA WIRE HARNESS TRAY LRM, GRP = 1 | 4.0667 | day | 0.24995 | hr | 4.0771 | day
| 733 | 337 | Release IEC-SC LRMs | 4.0979 | day | 0.75016 | hr | 4.1292 | day
| 730 | 337 | Release SC LRM GRP-05A/B, Pre-DTA Deploy +J2 IEC - S/C, Group = 1 | 4.0979 | day | 0.25008 | hr | 4.1083 | day
| 731 | 337 | Release SC LRM GRP-06A/B, Pre-DTA Deploy -J2 IEC - S/C, Group = 1 | 4.1188 | day | 0.25008 | hr | 4.1292 | day
| 551 | 337 | Release BSF-SC LRMs (3/4 inch) | 4.1604 | day | 1.0001 | hr | 4.2021 | day
| 565 | 337 | Release SC LRM GRP-07A/B, Pre-DTA Deploy +J1/+J2 BSF - S/C (3/4 inch), Group = 1 | 4.1604 | day | 0.12496 | hr | 4.1656 | day
| 568 | 337 | Release SC LRM GRP-010A/10B, Pre-DTA Deploy +J1/-J2 BSF - S/C (3/4 inch), Group = 1 | 4.1726 | day | 0.125 | hr | 4.1778 | day
| 567 | 337 | Release SC LRM GRP-09A/B, Pre-DTA Deploy -J1/-J2 BSF - S/C (3/4 inch), Group = 1 | 4.1847 | day | 0.12504 | hr | 4.1899 | day
| 566 | 337 | Release SC LRM GRP-08A/B, Pre-DTA Deploy -J1/+J2 BSF - S/C (3/4 inch), Group = 1 | 4.1969 | day | 0.12508 | hr | 4.2021 | day
| 689 | HEADER | DTA Deployment Operations | 4.2 | day | 6.87 | hr | 4.4862 | day
| 572 | 689 | DTA Deployment, Relax Preload & Drive Thru Backlast (1/5) & Verify Tower Motion & LRM Separation (2/5) | 4.2069 | day | 0.33333 | hr | 4.2208 | day
| 573 | 689 | DTA Deployment, Bulk Tower Deploy Part 1 (3/5) | 4.2278 | day | 2.5167 | hr | 4.3326 | day
| 574 | 689 | DTA Deployment, Bulk Tower Deploy Part 2 (4/5) | 4.3396 | day | 2.5167 | hr | 4.4444 | day
| 575 | 689 | DTA Deployment, Set Deployment Preload (5/5) | 4.4514 | day | 0.33333 | hr | 4.4653 | day
| 576 | 689 | Disable DTA Thermal Control Command DTA Deployment TCL to Manual, Turn OFF Deployment motor heaters | 4.4722 | day | 0.083333 | hr | 4.4757 | day
| 577 | 689 | Terminate ADU DTA temperature retrieval SCS | 4.4826 | day | 0.083333 | hr | 4.4861 | day
| 545 |  | Release CJAA / IEC +V3 LRM | 4.4931 | day | 0.24996 | hr | 4.5035 | day
| 911.04 |  | Enable Sunline Rotation | 4.5104 | day | 0.41667 | hr | 4.5278 | day
| 288 |  | SS UPS Relay TCLs | 4.5347 | day | 0.25008 | hr | 4.5451 | day
| 891.09 |  | Alarm Limit Transition #9 (Post DTA Deployment) | 4.5451 | day | 0.083333 | hr | 4.5486 | day
| 756.2 | NRS-33 | NIRSpec MSA Heater Adjustment #1 during Cooldown | 4.5556 | day | 0.3 | hr | 4.5681 | day
| 912.04 |  | Disable Sunline Rotation | 4.9722 | day | 0.55 | hr | 4.9951 | day
| 279 | HEADER | CCA Release | 5 | day | 0.83326 | hr | 5.0347 | day
| 579 | 279 | Release SC LRM GRP-19A/B, Cryocooler Support CC SPT ASSY +J1, SCLRM29, Group = 1 | 5 | day | 0.16659 | hr | 5.0069 | day
| 580 | 279 | Release SC LRM GRP-17A/B, Cryocooler Support CC SPT ASSY -J1 / -J2, SCLRM27, Group = 1 | 5.0139 | day | 0.16672 | hr | 5.0208 | day
| 581 | 279 | Release SC LRM GRP-18A/B, Cryocooler Support CC SPT ASSY -J1 / +J2, SCLRM28, Group = 1 | 5.0278 | day | 0.16662 | hr | 5.0347 | day
| 298 |  | Release Aft Momentum Flap | 5.05 | day | 0.49999 | hr | 5.0708 | day
| 880 |  | Motor Flinch Move Prior to SS Membrane Cover Release | 5.0778 | day | 2 | hr | 5.1611 | day
| 289 | HEADER | Release Sunshield Membrane Covers Up To Edges | 5.1681 | day | 5 | hr | 5.3764 | day
| 582 | 289 | Release SS MRD GRP-06A/B, Membrane Release NON-LADDER SMSS, AFT UPS -J3 SIDE, Group = 3 | 5.1681 | day | 0.24994 | hr | 5.1785 | day
| 583 | 289 | Release SS MRD GRP-07A/B, Membrane Release NON-LADDER +J2 TIP, AFT UPS -J3 SIDE, Group = 4 | 5.1785 | day | 0.2501 | hr | 5.1889 | day
| 584 | 289 | Release SS MRD GRP-08A/B, Membrane Release NON-LADDER -J2 TIP, AFT UPS -J3 SIDE, Group = 4 | 5.1889 | day | 0.24994 | hr | 5.1993 | day
| 585 | 289 | Release SS MRD GRP-09A/B, Membrane Release LADDER ASSEMBLY LOWER, AFT UPS -J3 SIDE, Group = 5 | 5.1993 | day | 0.25002 | hr | 5.2097 | day
| 586 | 289 | Release SS MRD GRP-10A/B, Membrane Release LADDER ASSEMBLY UPPER, AFT UPS -J3 SIDE, Group = 5 | 5.2097 | day | 0.2501 | hr | 5.2201 | day
| 587 | 289 | Release SS MRD GRP-11A/B, Membrane Release CENTER ROW, AFT UPS -J3 SIDE, Group = 5 | 5.2201 | day | 0.24994 | hr | 5.2306 | day
| 588 | 289 | Release SS MRD GRP-12A/B, Membrane Release -J2 MID ROW, AFT UPS -J3 SIDE, Group = 5 | 5.2306 | day | 0.25002 | hr | 5.241 | day
| 589 | 289 | Release SS MRD GRP-13A/B, Membrane Release -J2 EDGE ROW, AFT UPS -J3 SIDE, Group = 5 | 5.241 | day | 0.2501 | hr | 5.2514 | day
| 590 | 289 | Release SS MRD GRP-14A/B, Membrane Release +J2 MID ROW, AFT UPS -J3 SIDE, Group = 5 | 5.2514 | day | 0.24994 | hr | 5.2618 | day
| 591 | 289 | Release SS MRD GRP-15A/B, Membrane Release +J2 EDGE ROW, AFT UPS -J3 SIDE, Group = 5 | 5.2618 | day | 0.25002 | hr | 5.2722 | day
| 592 | 289 | Release SS MRD GRP-16A/B, Membrane Release NON-LADDER AOS BAFFLE, FWD UPS -J3 SIDE, Group = 5 | 5.2722 | day | 0.2501 | hr | 5.2826 | day
| 593 | 289 | Release SS MRD GRP-17A/B, Membrane Release NON-LADDER UPPER, FWD UPS -J3 SIDE, Group = 5 | 5.2826 | day | 0.24994 | hr | 5.2931 | day
| 594 | 289 | Release SS MRD GRP-18A/B, Membrane Release LADDER ASSEMBLY, FWD UPS -J3 SIDE, Group = 5 | 5.2931 | day | 0.25002 | hr | 5.3035 | day
| 595 | 289 | Release SS MRD GRP-19A/B, Membrane Release CENTER ROW, FWD UPS -J3 SIDE, Group = 5 | 5.3035 | day | 0.2501 | hr | 5.3139 | day
| 596 | 289 | Release SS MRD GRP-20A/B, Membrane Release -J2 MID ROW, FWD UPS -J3 SIDE, Group = 5 | 5.3139 | day | 0.24994 | hr | 5.3243 | day
| 597 | 289 | Release SS MRD GRP-21A/B, Membrane Release -J2 EDGE ROW, FWD UPS -J3 SIDE, Group = 5 | 5.3243 | day | 0.25002 | hr | 5.3347 | day
| 598 | 289 | Release SS MRD GRP-22A/B, Membrane Release +J2 MID ROW, FWD UPS -J3 SIDE, Group = 5 | 5.3347 | day | 0.2501 | hr | 5.3452 | day
| 599 | 289 | Release SS MRD GRP-23A/B, Membrane Release +J2 EDGE ROW, FWD UPS -J3 SIDE, Group = 5 | 5.3452 | day | 0.24994 | hr | 5.3556 | day
| 600 | 289 | Release SS MRD GRP-24A/B, Membrane Release -J2 CORE COVER RESTRAINT GROUP, +J3/-J2 SIDE OF +J3 PANEL, Group = 2 | 5.3556 | day | 0.25002 | hr | 5.366 | day
| 601 | 289 | Release SS MRD GRP-25A/B, Membrane Release +J2 CORE COVER RESTRAINT GROUP, +J3/+J2 SIDE OF +J3 PANEL, Group = 2 | 5.366 | day | 0.2501 | hr | 5.3764 | day
| 911.05 |  | Enable Sunline Rotation | 5.3834 | day | 0.41667 | hr | 5.4007 | day
| 756.3 | NRS-33 | NIRSpec MSA Heater Adjustment #2 during Cooldown | 5.75 | day | 0.3 | hr | 5.7625 | day
| 912.05 |  | Disable Sunline Rotation | 5.9722 | day | 0.55 | hr | 5.9951 | day
| 724 | HEADER | Sunshield +J2 Midboom Operations | 6 | day | 5 | hr | 6.2083 | day
| 290 | 724 | Release SS LRM GRP-06A/B, MID-BOOM TO SB/MTS LRM, (+J2/+J1, +J2/-J1, +J2/+J3), GRP = 3 | 6 | day | 0.25002 | hr | 6.0104 | day
| 546 | 724 | Release DRSA-H (+J2) | 6.0174 | day | 0.58293 | hr | 6.0417 | day
| 602 | 724 | Release SS MRD GRP-29A/B, +J1/+J2 HORIZONTAL RADIATOR SHADE MRD, Group = 1 | 6.0174 | day | 0.2501 | hr | 6.0278 | day
| 603 | 724 | Release SS MRD GRP-31A/B, -J1/+J2 HORIZONTAL RADIATOR SHADE MRD, Group = 1 | 6.0347 | day | 0.24994 | hr | 6.0451 | day
| 25 | 724 | Sunshield Pushout +J2 Midboom | 6.0521 | day | 2.3333 | hr | 6.1493 | day
| 291 | 724 | Sunshield +J2 Midboom Stem Reel-in | 6.1563 | day | 0.33333 | hr | 6.1701 | day
| 725 | HEADER | Sunshield -J2 Midboom Operations | 6.2292 | day | 4.17 | hr | 6.4029 | day
| 292 | 725 | Release SS LRM GRP-05A/B, MID-BOOM TO SB/MTS LRM, (-J2/-J1, -J2/+J1, -J2/+J3), GRP = 3 | 6.2292 | day | 0.25007 | hr | 6.2396 | day
| 547 | 725 | Release DRSA-H (-J2) | 6.25 | day | 0.099421 | hr | 6.2541 | day
| 604 | 725 | Release SS MRD GRP-30A/B, +J1/-J2 HORIZONTAL RADIATOR SHADE MRD, Group = 1 | 6.25 | day | 0.25008 | hr | 6.2604 | day
| 605 | 725 | Release SS MRD GRP-32A/B, -J1/-J2 HORIZONTAL RADIATOR SHADE MRD, Group = 1 | 6.2708 | day | 0.24992 | hr | 6.2813 | day
| 293 | 725 | Sunshield Pushout -J2 Midboom | 6.2813 | day | 2.3333 | hr | 6.3785 | day
| 294 | 725 | Sunshield -J2 Midboom Stem Reel-in | 6.3889 | day | 0.33333 | hr | 6.4028 | day
| 891.10 |  | Alarm Limit Transition #10 (Post Midboom Deploy) | 6.4 | day | 0.083333 | hr | 6.4035 | day
| 911.06 |  | Enable Sunline Rotation | 6.4104 | day | 0.41667 | hr | 6.4278 | day
| 912.06 |  | Disable Sunline Rotation | 6.9722 | day | 0.55 | hr | 6.9951 | day
| 908 |  | Midboom Snubber Release Motor Moves | 7 | day | 1.15 | hr | 7.0479 | day
| 295 | HEADER | Sunshield Rim LRM Release | 7.0549 | day | 0.5 | hr | 7.0757 | day
| 606 | 295 | Release SS LRM GRP-07A/B, RIM/PLATEN RIM/PLATEN HOLD-DOWN LRM, LRM-13&14, Group = 2 | 7.0549 | day | 0.25 | hr | 7.0653 | day
| 607 | 295 | Release SS LRM GRP-08A/B, RIM/PLATEN RIM/PLATEN HOLD-DOWN LRM, LRM-15 to 19, Group = 5 | 7.0653 | day | 0.25004 | hr | 7.0757 | day
| 909 | HEADER | Cable Brake LRM Release + Initial MTS Reel In | 7.0826 | day | 0.5 | hr | 7.1035 | day
| 608 | 909 | Release SS MRD GRP-26A/B, Cable Brake +J1 / ±J2 SPREADER BAR CABLE RESTRAINT (FWD CABLE BRAKE PAIR), MRD-26, Group = 2 | 7.0757 | day | 0.25012 | hr | 7.0861 | day
| 609 | 909 | Release SS MRD GRP-27A/B, Cable Brake -J1 / ±J2 SPREADER BAR CABLE RESTRAINT (AFT CABLE BRAKE PAIR), MRD-27, Group = 2 | 7.0861 | day | 0.24996 | hr | 7.0965 | day
| 610 | HEADER | Membrane Tension Layer 1 | 7.1104 | day | 2.8 | hr | 7.2271 | day
| 296 | 610 | Sunshield Membrane Tensioning Sequence | 7.1104 | day | 28.3033 | hr | 8.2897 | day
| 611 | 610 | Membrane Tension Layer 1: (-J2 MTS) Motor #7 | 7.1104 | day | 0.1 | hr | 7.1146 | day
| 612 | 610 | Membrane Tension Layer 1: (Fwd MTS Pair) Motor #10, #11 | 7.1215 | day | 1 | hr | 7.1632 | day
| 613 | 610 | Membrane Tension Layer 1: (Aft MTS Pair) Motor #8, #9 | 7.1701 | day | 1.1667 | hr | 7.2188 | day
| 911.07 |  | Enable Sunline Rotation | 7.2257 | day | 0.41667 | hr | 7.2431 | day
| 756.4 | NRS-33 | NIRSpec MSA Heater Adjustment #3 during Cooldown | 7.5 | day | 0.3 | hr | 7.5125 | day
| 912.07 |  | Disable Sunline Rotation | 7.9722 | day | 0.55 | hr | 7.9951 | day
| 614 | HEADER | Membrane Tension Layer 2 | 8 | day | 1.7 | hr | 8.0708 | day
| 615 | 614 | Membrane Tension Layer 2: -J2 MTS Motor #7 | 8 | day | 0.1 | hr | 8.0042 | day
| 616 | 614 | Membrane Tension Layer 2: +/-J2 Fwd UPS MTS Pair Motor #10, #11 | 8.0111 | day | 0.41667 | hr | 8.0285 | day
| 617 | 614 | Membrane Tension Layer 2: +/-J2 Aft UPS MTS Pair Motor #8, #9 | 8.0354 | day | 0.58333 | hr | 8.0597 | day
| 618 | HEADER | Membrane Tension Layer 3 | 8.0778 | day | 1.7 | hr | 8.1486 | day
| 619 | 618 | Membrane Tension Layer 3: -J2 MTS Motor #7 | 8.08 | day | 0.1 | hr | 8.0842 | day
| 620 | 618 | Membrane Tension Layer 3: +/-J2 Fwd UPS MTS Pair Motor #10, #11 | 8.0911 | day | 0.41667 | hr | 8.1085 | day
| 621 | 618 | Membrane Tension Layer 3: +/-J2 Aft UPS MTS Pair Motor #8, #9 | 8.1154 | day | 0.58333 | hr | 8.1397 | day
| 622 | HEADER | Membrane Tension Layer 4 | 8.1556 | day | 1.7 | hr | 8.2264 | day
| 623 | 622 | Membrane Tension Layer 4: -J2 MTS Motor #7 | 8.16 | day | 0.1 | hr | 8.1642 | day
| 624 | 622 | Membrane Tension Layer 4: +/-J2 Fwd UPS MTS Pair Motor #10, #11 | 8.1711 | day | 0.41667 | hr | 8.1885 | day
| 625 | 622 | Membrane Tension Layer 4: +/-J2 Aft UPS MTS Pair Motor #8, #9 | 8.1954 | day | 0.58333 | hr | 8.2197 | day
| 626 | HEADER | Membrane Tension Layer 5 | 8.2333 | day | 1.7 | hr | 8.3042 | day
| 627 | 626 | Membrane Tension Layer 5: -J2 MTS Motor #7 | 8.23 | day | 0.1 | hr | 8.2342 | day
| 628 | 626 | Membrane Tension Layer 5: +/-J2 Fwd UPS MTS Pair Motor #10, #11 | 8.2411 | day | 0.41667 | hr | 8.2585 | day
| 629 | 626 | Membrane Tension Layer 5: +/-J2 Aft UPS MTS Pair Motor #8, #9 | 8.2654 | day | 0.58333 | hr | 8.2897 | day
| 891.11 |  | Alarm Limit Transition #11 (Post SS Membrane Deploy) | 8.3042 | day | 0.083333 | hr | 8.3076 | day
| 297 |  | Sunshield Disable MTS Gearmotor heaters | 8.3146 | day | 0.083333 | hr | 8.3181 | day
| 299 |  | Power OFF Sunshield heaters | 8.325 | day | 0.0166 | hr | 8.3257 | day
| 911.08 |  | Enable Sunline Rotation | 8.3326 | day | 0.41667 | hr | 8.35 | day
| 912.08 |  | Disable Sunline Rotation | 8.97 | day | 0.55 | hr | 8.9929 | day
| 26 | HEADER | DRSA-V Deployment | 8.9999 | day | 0.75001 | hr | 9.0311 | day
| 553 | 26 | Release SC LRM GRP-15A/B, Vertical Radiator Shade +J1/+J2 VERTICAL RADIATOR SHADE LRM, Group = 2 | 8.9999 | day | 0.25009 | hr | 9.0103 | day
| 554 | 26 | Release SC LRM GRP-16A/B, Vertical Radiator Shade +J1/-J2 VERTICAL RADIATOR SHADE LRM, Group = 2 | 9.0207 | day | 0.24993 | hr | 9.0311 | day
| 252 |  | Release SC LRM GRP-03A/B, STSA STAR TRACKER SUPPORT STRUCTURE UPPER LAUNCH LOCK STA RADIATOR Group = 3 | 9.0415 | day | 0.016725 | hr | 9.0422 | day
| 257 |  | SMSS Deployment Motor Heating | 9.0492 | day | 21 | hr | 9.9242 | day
| 911.09 |  | Enable Sunline Rotation | 9.0631 | day | 0.41667 | hr | 9.0805 | day
| 61 |  | Cryocooler Power ON and Transition to State 2 (Internal Decontamination) | 9.0875 | day | 2.92 | hr | 9.2091 | day
| 18.1 |  | MIRI ICE Power ON and Initialization | 9.2161 | day | 0.28 | hr | 9.2278 | day
| 764.1 | MIR-71 | MIRI ICE Warm Basic Functional Test | 9.2347 | day | 0.63 | hr | 9.2609 | day
| 19 | MIR-42.1 | MIRI CCC Unlock and Opening | 9.2679 | day | 0.2 | hr | 9.2762 | day
| 866 |  | MIRI ICE Power OFF | 9.2832 | day | 0.27 | hr | 9.2944 | day
| 912.09 |  | Disable Sunline Rotation | 9.9103 | day | 0.55 | hr | 9.9333 | day
| 691 | HEADER | SMSS Deployment Operations | 9.9242 | day | 7.2355 | hr | 10.2257 | day
| 878 | 691 | Synch Mid-hinge Latch Stepper Motor & Flinch move for Inboard Hinge | 9.9242 | day | 1 | hr | 9.9659 | day
| 28 | 691 | Release SMSS LRMs | 10 | day | 0.72 | hr | 10.03 | day
| 632 | 691 | Release OTE LRM GRP-03A/B, SMSS (PMBA SIDE) SMSS TO +V2 DUAL LRM | 10 | day | 0.24998 | hr | 10.0104 | day
| 633 | 691 | Release OTE LRM GRP-05A/B, , SMSS (PMBA SIDE) SMSS TO SINGLE STRUT LRM, Group = 1 | 10.0174 | day | 0.25006 | hr | 10.0278 | day
| 300 | 691 | SMSS First motion | 10.0347 | day | 0.24997 | hr | 10.0451 | day
| 301 | 691 | SMSS Deployment | 10.0521 | day | 1.0001 | hr | 10.0938 | day
| 302 | 691 | SMSS Latch Bulk move | 10.1007 | day | 1 | hr | 10.1424 | day
| 304 | 691 | Remove SMSS holding torque | 10.1493 | day | 0.25003 | hr | 10.1597 | day
| 305 | 691 | Back off SMSS hinge | 10.1667 | day | 0.25011 | hr | 10.1771 | day
| 303 | 691 | SMSS Latch Terminal move | 10.184 | day | 0.49995 | hr | 10.2049 | day
| 306 | 691 | Power OFF SMSS heaters | 10.2118 | day | 0.33333 | hr | 10.2257 | day
| 891.12 |  | Alarm Limit Transition #12 (Post SMSS Deploy) | 10.2257 | day | 0.083333 | hr | 10.2292 | day
| 911.10 |  | Enable Sunline Rotation | 10.2361 | day | 0.41667 | hr | 10.2535 | day
| 636 |  | ADIR Launch Lock Heating | 10.2604 | day | 18 | hr | 11.0104 | day
| 747 |  | Adjust Spacecraft Thermal Stability Heater Set-points | 10.5 | day | 0.5 | hr | 10.5208 | day
| 912.10 |  | Disable Sunline Rotation | 10.9822 | day | 0.55 | hr | 11.0051 | day
| 282 | HEADER | ADIR Launch Lock Release Part 2 | 11.01 | day | 1 | hr | 11.0417 | day
| 637 | 282 | Release OTE LRM GRP-09A/B, ADIR Part 2 ADIR -V2/+V3, Part 2, Group = 1 | 11 | day | 1 | hr | 11.0417 | day
| 911.11 |  | Enable Sunline Rotation | 11.0486 | day | 0.41667 | hr | 11.066 | day
| 260 |  | PMBA (+V2) Motor Heating | 11.0729 | day | 18 | hr | 11.8229 | day
| 912.11 |  | Disable Sunline Rotation | 11.9722 | day | 0.55 | hr | 11.9951 | day
| 692 | HEADER | PMBA +V2 Deployment Operations | 12 | day | 10.8506 | hr | 12.4521 | day
| 877 | 692 | Synch PMBA Latch Stepper Motor & Perform Flinch Move on PMBA Drive Hinge | 12 | day | 1 | hr | 12.0417 | day
| 307 | 692 | PMBA (+V2) Wing Release | 12.0486 | day | 0.66659 | hr | 12.0764 | day
| 640 | 692 | Release OTE LRM GRP-04A/B, PMBA +V2 Wing (BSF SIDE) PMBA (BSF) TO +V2 WING +V1/+V3 LRM | 12.0486 | day | 0.25004 | hr | 12.059 | day
| 641 | 692 | Release OTE LRM GRP-06A/B, , PMBA +V2 Wing (BSF SIDE) PMBA (BSF) TO +V2 WING -V1/+V3 LRM | 12.066 | day | 0.24988 | hr | 12.0764 | day
| 308 | 692 | PMBA (+V2) Wing First Motion | 12.0833 | day | 0.50011 | hr | 12.1042 | day
| 29 | 692 | PMBA (+V2) Wing Deployment | 12.1111 | day | 1.3 | hr | 12.1653 | day
| 726 | 692 | PMBA (+V2) Wing Latch Sequence | 12.1722 | day | 6.0004 | hr | 12.4222 | day
| 309 | 692 | PMBA +V2 3-DOR Cup Latch bulk Move (1 of 8) (DEU hold preload, ADU motor move) | 12.1722 | day | 0.50011 | hr | 12.1931 | day
| 310 | 692 | PMBA +V2 2-DOR Groove Latch bulk Move (2 of 8) (DEU hold preload, ADU motor move) | 12.2 | day | 0.50003 | hr | 12.2208 | day
| 311 | 692 | PMBA +V2 3-DOR Cup Latch Terminal Move and Latch (3 of 8) (DEU hold preload, ADU motor move) | 12.2278 | day | 0.49995 | hr | 12.2486 | day
| 312 | 692 | PMBA +V2 2-DOR Groove Latch Terminal Move and Latch (4 of 8 (DEU hold preload, ADU motor move) | 12.2556 | day | 0.50011 | hr | 12.2764 | day
| 313 | 692 | PMBA +V2 Top (+V3) 1-DOR Flat bulk Move (5 of 8) (DEU hold preload, ADU motor move) | 12.2833 | day | 0.50003 | hr | 12.3042 | day
| 314 | 692 | PMBA +V2 Top (+V3) 1-DOR Flat Terminal Move and Latch (6 of 8) (DEU hold preload, ADU motor move) | 12.3111 | day | 0.49995 | hr | 12.332 | day
| 315 | 692 | PMBA +V2 Bottom (-V3) 1-DOR Flat bulk Move (7 of 8) (DEU hold preload, ADU motor move) | 12.3389 | day | 0.50011 | hr | 12.3597 | day
| 316 | 692 | PMBA +V2 Bottom (-V3) 1-DOR Flat Terminal Move and Latch (8 of 8) (DEU hold preload, ADU motor move) | 12.3667 | day | 0.50003 | hr | 12.3875 | day
| 317 | 692 | Remove PMBA +V2 deployment holding torque (DEU motor move) | 12.3945 | day | 0.25011 | hr | 12.4049 | day
| 332 | 692 | Back off PMBA +V2 deployment to relieve force at hinge (DEU motor move) | 12.4118 | day | 0.24995 | hr | 12.4222 | day
| 319 | 692 | Power OFF PMBA (+V2) heaters | 12.4292 | day | 0.3 | hr | 12.4417 | day
| 318 | 692 | Command ADU to Operate Mode and inhibit motor moves | 12.4417 | day | 0.25009 | hr | 12.4521 | day
| 911.12 |  | Enable Sunline Rotation | 12.4591 | day | 0.41667 | hr | 12.4764 | day
| 259 |  | PMBA (-V2) Motor Heating | 12.4834 | day | 18 | hr | 13.2334 | day
| 912.12 |  | Disable Sunline Rotation | 13.2056 | day | 0.55 | hr | 13.2285 | day
| 693 | HEADER | PMBA -V2 Deployment Operations | 13.2334 | day | 11.3504 | hr | 13.7063 | day
| 876 | 693 | Synch PMBA Latch Stepper Motor & Perform Flinch Move on PMBA Drive Hinge | 13.2334 | day | 1 | hr | 13.275 | day
| 320 | 693 | PMBA (-V2) Release | 13.282 | day | 1.333 | hr | 13.3375 | day
| 646 | 693 | Release OTE LRM GRP-07A/B, PMBA -V2 Wing (BSF SIDE) PMBA (BSF) TO -V2 WING +V1/+V3 LRM Group = 2 | 13.282 | day | 0.5 | hr | 13.3028 | day
| 647 | 693 | Release OTE LRM GRP-08A/B, PMBA -V2 Wing (BSF SIDE) PMBA (BSF) TO -V2 WING -V1/+V3 LRM Group = 2 | 13.3097 | day | 0.49992 | hr | 13.3306 | day
| 321 | 693 | PMBA (-V2) First Motion | 13.3375 | day | 0.49993 | hr | 13.3584 | day
| 322 | 693 | PMBA (-V2) Deployment | 13.3653 | day | 1.3 | hr | 13.4195 | day
| 727 | 693 | PMBA (-V2) Wing Latch Sequence | 13.4264 | day | 6.0004 | hr | 13.6764 | day
| 323 | 693 | PMBA -V2 3-DOR Cup Latch bulk Move (1 of 8) (DEU hold preload, ADU motor move) | 13.4264 | day | 0.50008 | hr | 13.4472 | day
| 324 | 693 | PMBA -V2 2-DOR Groove Latch bulk Move (2 of 8) (DEU hold preload, ADU motor move) | 13.4542 | day | 0.50007 | hr | 13.475 | day
| 325 | 693 | PMBA -V2 3-DOR Cup Latch Terminal Move and Latch (3 of 8) (DEU hold preload, ADU motor move) | 13.482 | day | 0.50006 | hr | 13.5028 | day
| 326 | 693 | PMBA -V2 2-DOR Groove Latch Terminal Move and Latch (4 of 8) (DEU hold preload, ADU motor move) | 13.5097 | day | 0.50005 | hr | 13.5306 | day
| 327 | 693 | PMBA -V2 Top (+V3) 1-DOR Flat bulk Move (5 of 8) (DEU hold preload, ADU motor move) | 13.5375 | day | 0.50005 | hr | 13.5584 | day
| 328 | 693 | PMBA -V2 Top (+V3) 1-DOR Flat Terminal Move and Latch (6 of 8) (DEU hold preload, ADU motor move) | 13.5653 | day | 0.50004 | hr | 13.5861 | day
| 329 | 693 | PMBA -V2 Bottom (-V3) 1-DOR Flat bulk Move (7 of 8) (DEU hold preload, ADU motor move) | 13.5931 | day | 0.50003 | hr | 13.6139 | day
| 330 | 693 | PMBA -V2 Bottom (-V3) 1-DOR Flat Terminal Move and Latch (8 of 8) (DEU hold preload, ADU motor move) | 13.6209 | day | 0.50002 | hr | 13.6417 | day
| 331 | 693 | Remove PMBA -V2 deployment holding torque (DEU motor move) | 13.6486 | day | 0.24993 | hr | 13.6591 | day
| 552 | 693 | Back off PMBA -V2 deployment to relieve force at hinge (DEU motor move) | 13.666 | day | 0.25009 | hr | 13.6764 | day
| 333 | 693 | Power OFF PMBA (-V2) heaters | 13.6834 | day | 0.3 | hr | 13.6959 | day
| 550 | 693 | Command ADU to Operate Mode and inhibit motor moves | 13.6959 | day | 0.25009 | hr | 13.7063 | day
| 891.13 |  | Alarm Limit Transition #13 (Post PMBA Deploy) | 13.7063 | day | 0.083333 | hr | 13.7098 | day
| 916.2 |  | Higher Bus Voltage for Deployments | 13.7168 | day | 0.16667 | hr | 13.7237 | day
| 865 |  | Reconfigure Cryocooler Knock Trip Thresholds | 13.8063 | day | 0.6 | hr | 13.8313 | day
| 864 |  | ADU Reset & FSM Controller State post 3/4" NEA Release + Disable FSM Cal | 13.8382 | day | 0.25 | hr | 13.8486 | day
| 875 |  | Enable Sunline Rotation | 13.8556 | day | 0.083333 | hr | 13.8591 | day
| 841 |  | Set ACS Control System Gains for Post Deployments | 13.9291 | day | 0.25 | hr | 13.9395 | day
| 780 |  | IRSU MSC Power ON and Configuration | 14 | day | 0.4 | hr | 14.0167 | day
| 49 |  | ACS Calibration (STA) | 14.0567 | day | 6 | hr | 14.3067 | day
| 885 |  | COMM Reconfiguration prior to IRU Calibration | 14.3467 | day | 0.25 | hr | 14.3571 | day
| 892 |  | IRU Calibration and Inertia Estimation | 14.3971 | day | 4 | hr | 14.5637 | day
| 892 |  | IRU Calibration - Analysis | 14.5637 | day | 5 | hr | 14.7721 | day
| 886 |  | COMM Reconfiguration after IRU Calibration | 14.7721 | day | 0.25 | hr | 14.7825 | day
| 893 |  | ACS Calibration (FSS) | 14.8225 | day | 7 | hr | 15.1142 | day
| 861 |  | DITCE Power & FSM Initialization | 15.1542 | day | 0.5 | hr | 15.175 | day
| 903.1 |  | OTE FSM Stability & Spiral Scan | 15.1819 | day | 4 | hr | 15.3486 | day
| 32 | OTE-00 | PMSAs & SMA Deployment | 15.5 | day | 235 | hr | 25.2917 | day
| 153 |  | OTE Temperature Collection (every 12 hours for 100 days) | 15.5 | day | 0.17 | hr | 15.5071 | day
| 18.2 |  | MIRI ICE Power ON and Initialization | 15.6071 | day | 0.33 | hr | 15.6208 | day
| 764.2 | MIR-71 | MIRI ICE Warm Basic Functional Test | 15.7208 | day | 0.63 | hr | 15.7471 | day
| 815 |  | MIRI FPE Power ON | 15.8471 | day | 0.22 | hr | 15.8562 | day
| 125.1 | MIR-01.1 | MIRI Focal Plane System Warm Checkout | 15.9562 | day | 1.28 | hr | 16.0096 | day
| 756.5 | NRS-33 | NIRSpec MSA Heater Adjustment #4 during Cooldown | 16.0496 | day | 0.3 | hr | 16.0621 | day
| 125.1 | MIR-01.1 | MIRI Focal Plane System Warm Checkout | 17.87 | day | 0.35 | hr | 17.8846 | day
| 817 | MIR-42.2 | MIRI FPM Heater Power ON during Cooldown | 17.9 | day | 0.39 | hr | 17.9162 | day
| 37 | MIR-42.3 | MIRI CCC Closure | 22.5 | day | 0.35 | hr | 22.5146 | day
| 887.1 | MIR-42.4 | Start MIRI POM Cooldown Operations | 22.5146 | day | 0.3 | hr | 22.5271 | day
| 756.6 | NRS-33 | NIRSpec MSA Heater Adjustment #5 during Cooldown | 23.8 | day | 0.3 | hr | 23.8125 | day
| 14 |  | Ka-Band Activation | 25.2986 | day | 1 | hr | 25.3403 | day
| 891.14 |  | Alarm Limit Transition #14 (Post Ka-Band Activation) | 25.3403 | day | 0.083333 | hr | 25.3437 | day
| 913.1 |  | HGA Calibration 0 (SCSes required to execute over 1 DSN contact) | 25.3507 | day | 9 | hr | 25.7257 | day
| 913.1 |  | HGA Calibration 0 - analysis | 25.7257 | day | 16 | hr | 26.3924 | day
| 760 | NRS-34 | NIRSpec FPE Power ON & ASIC Initialization | 25.8257 | day | 0.83 | hr | 25.8603 | day
| 761 | NRS-36 | NIRSpec ICE Power ON | 25.9603 | day | 0.4 | hr | 25.977 | day
| 913.2 |  | HGA Calibration 0 (Required to execute over 1 DSN contact) | 26.3924 | day | 2 | hr | 26.4757 | day
| 913.2 |  | HGA Calibration 0 - analysis | 26.4757 | day | 6 | hr | 26.7257 | day
| 334.1 |  | HGA Calibration 1 (SCSes required to execute over 1 DSN contact) | 26.7257 | day | 9 | hr | 27.1007 | day
| 334.1 |  | HGA Calibration 1 - analysis | 27.1007 | day | 16 | hr | 27.7674 | day
| 334.2 |  | HGA Calibration 1 (Required to execute over 1 DSN contact) | 27.7674 | day | 2 | hr | 27.8507 | day
| 334.2 |  | HGA Calibration 1 - analysis | 27.8507 | day | 6 | hr | 28.1007 | day
| 917 |  | Nominal Flight Packet List & Filter Tables | 28.1077 | day | 2 | hr | 28.191 | day
| 50 |  | Initial Ka-band PB | 28.198 | day | 3 | hr | 28.323 | day
| 55 |  | MCC2 (Burn at L+29d) | 28.6667 | day | 10 | hr | 29.0833 | day
| 889 |  | OPE Activation without Momentum Monitoring | 30 | day | 0.35 | hr | 30.0146 | day
| 898 |  | Enable JPIM ISIM Overrun Fault Response | 30.0146 | day | 0.083333 | hr | 30.0181 | day
| 125.2 | MIR-01.2 | MIRI Focal Plane System Warm Checkout | 30.0181 | day | 2.13 | hr | 30.1068 | day
| 872 |  | Stubbing Out Post-Launch SCSs | 30.1068 | day | 0.5 | hr | 30.1276 | day
| 923 |  | EEPROM Load Clean-up | 30.1276 | day | 1 | hr | 30.1693 | day
| 894 |  | 7M & 14M Ka-Band Rate Characterization | 30.1693 | day | 0.5 | hr | 30.1901 | day
| 33 |  | Disable Autonomous On-board Control of IRSU CCH Zones 1-4 | 31.65 | day | 0.8 | hr | 31.6833 | day
| 748 |  | Solar Torque Calibration | 31.6833 | day | 52 | hr | 33.85 | day
| 890 |  | Enable OPE Momentum Control | 33.85 | day | 0.18 | hr | 33.8575 | day
| 820 | NIS-00 | NIRISS Power ON | 33.8575 | day | 0.2 | hr | 33.8658 | day
| 340 | NIS-01 | NIRISS Initialization | 33.8658 | day | 0.45 | hr | 33.8846 | day
| 852 | FGS-00 | FGS Power ON | 33.8846 | day | 0.26 | hr | 33.8954 | day
| 151 | FGS-01 | FGS Initialization | 33.8954 | day | 0.73 | hr | 33.9258 | day
| 756.7 | NRS-33 | NIRSpec MSA Heater Deactivation after Cooldown | 34.95 | day | 0.16 | hr | 34.9567 | day
| 95 | NRS-04 | NIRSpec Detector System checkout | 34.9567 | day | 1.01 | hr | 34.9988 | day
| 926 |  | OSS RAM Update (Load 8.3) | 34.9988 | day | 1.5 | hr | 35.0613 | day
| 47 | NRC-01 | NIRCam Power ON | 35.76 | day | 0.52 | hr | 35.7817 | day
| 56 | NRC-02 | NIRCam Initialization | 35.7817 | day | 2.86 | hr | 35.9008 | day
| 58.1 | NRC-03 | NIRCam Initial Functional Check | 35.9008 | day | 2.97 | hr | 36.0246 | day
| 58.1 | NRC-03 | NIRCam Initial Function Check - Analysis | 36.0246 | day | 8 | hr | 36.3579 | day
| 170.1 |  | Momentum Unload (if needed) | 36.2129 | day | 3.48 | hr | 36.3579 | day
| 66 | OTE-01 | Initial Image Mosaic | 36.3579 | day | 35.72 | hr | 37.8462 | day
| 66 | OTE-01 | Initial Image Mosaic - Analysis | 37.8462 | day | 9 | hr | 38.2212 | day
| 849 |  | Load IRSU CCH Parameter Set 8 | 37.99 | day | 0.48 | hr | 38.01 | day
| 176 | OTE-02 | STA-FGS Alignment Matrix Update 1 (for DTA Deploy Errors) | 38.2212 | day | 1.52 | hr | 38.2846 | day
| 176 | OTE-02 | STA-FGS Alignment Matrix Update 1 (for DTA Deploy Errors) - Analysis | 38.2846 | day | 5.5 | hr | 38.5137 | day
| 58.2 | NRC-03 | NIRCam Initial Functional Check | 38.5137 | day | 1.73 | hr | 38.5858 | day
| 135 |  | Cryocooler Transition to State 3 (Precooler Cooldown) | 38.5858 | day | 0.43 | hr | 38.6037 | day
| 899.1 | NRC-35 | NIRCam Ice Measurement (pre FSM power-off) | 40.7 | day | 2.95 | hr | 40.8229 | day
| 899.1 | NRC-35 | NIRCam Ice Meausuremnt - Analysis | 40.8229 | day | 8 | hr | 41.1563 | day
| 814 |  | CAM for FSM Heater Power OFF | 41.1563 | day | 1 | hr | 41.1979 | day
| 814 |  | FSM Heater Power OFF | 41.1979 | day | 0.27 | hr | 41.2092 | day
| 895.1 |  | Final HGA Calibration | 41.5 | day | 9 | hr | 41.875 | day
| 895.1 |  | Final HGA Calibration - Analysis | 41.875 | day | 16 | hr | 42.5417 | day
| 341 | NIS-02 | NIRISS Aliveness and Functional Tests | 41.875 | day | 2.2 | hr | 41.9667 | day
| 162 | FGS-02 | FGS Aliveness and Functional Tests | 41.9667 | day | 1.75 | hr | 42.0396 | day
| 895.2 |  | Final HGA Calibration | 42.5417 | day | 2 | hr | 42.625 | day
| 895.2 |  | Final HGA Calibration - Analysis | 42.625 | day | 6 | hr | 42.875 | day
| 899.2 | NRC-35 | NIRCam Ice Measurement | 43 | day | 1.15 | hr | 43.0479 | day
| 175 | OTE-03 | Secondary Mirror Focus Sweep | 44.13 | day | 5.4 | hr | 44.355 | day
| 175 | OTE-03 | Secondary Mirror Focus Sweep - Analysis | 44.355 | day | 11.5 | hr | 44.8342 | day
| 174 | OTE-04 | Segment Identification | 44.8342 | day | 8.87 | hr | 45.2037 | day
| 850 |  | Load IRSU CCH Parameter Set 9 | 44.88 | day | 0.48 | hr | 44.9 | day
| 174 | OTE-04 | Segment Identification - Analysis | 45.2037 | day | 29.67 | hr | 46.44 | day
| 755 | NRS-37 | NIRSpec MCE Initialization | 45.4 | day | 2.03 | hr | 45.4846 | day
| 82 | NRS-02 | NIRSpec MSS Launch Lock Release and Magnet Arm Functional Verification | 45.54 | day | 0.59 | hr | 45.5646 | day
| 858 | MIR-42.5 | MIRI FPM Heater 1st Adjustment | 46.13 | day | 0.39 | hr | 46.1463 | day
| MILESTONE |  | Segment ID Complete | 46.44 | day | 0 | hr | 46.44 | day
| 177 | OTE-05 | STA-FGS Alignment Matrix Update 2 (for Segment Deploy Errors) | 46.44 | day | 1.52 | hr | 46.5033 | day
| 177 | OTE-05 | STA-FGS Alignment Matrix Update 2 - Analysis | 46.5033 | day | 5.5 | hr | 46.7325 | day
| 170.2 |  | Momentum Unload (if needed) | 46.5867 | day | 3.48 | hr | 46.7317 | day
| 171 | OTE-06 | Segment Image Array 1 | 46.7325 | day | 5.48 | hr | 46.9608 | day
| 171 | OTE-06 | Segment Image Array 1 - Analysis | 46.9608 | day | 11.5 | hr | 47.44 | day
| 899.3 | NRC-35 | NIRCam Ice Measurement | 47.44 | day | 3.5 | hr | 47.5858 | day
| 862.1 |  | Stationkeeping maneuver | 49 | day | 3.3333 | hr | 49.1389 | day
| 840 | LOS-02 | ACS Fine Guidance Control Verification | 49.47 | day | 2.5 | hr | 49.5742 | day
| 840 | LOS-02 | ACS Fine Guidance Control Verification - Analysis | 49.5742 | day | 5 | hr | 49.7825 | day
| MILESTONE |  | First Closed Loop Guiding | 49.7825 | day | 0.001 | hr | 49.7825 | day
| 172 | OTE-07 | Global Alignment 1 | 49.7825 | day | 12.43 | hr | 50.3004 | day
| 172 | OTE-07 | Global Alignment 1 - Analysis | 50.3004 | day | 27.5 | hr | 51.4462 | day
| 343 | NIS-04 | NIRISS Pupil Wheel Calibration | 50.3004 | day | 1.71 | hr | 50.3717 | day
| 343 | NIS-04 | NIRSS Pupil Wheel Calibration - Ground Analysis | 50.3717 | day | 12 | hr | 50.8717 | day
| 899.4 | NRC-35 | NIRCam Ice Measurement | 50.3717 | day | 1.16 | hr | 50.42 | day
| 344 | NIS-05 | NIRISS Filter Wheel Calibration | 50.8717 | day | 1.84 | hr | 50.9483 | day
| 344 | NIS-05 | NIRSS Filter Wheel Calibration - Ground Analysis | 50.9483 | day | 24 | hr | 51.9483 | day
| 178 | OTE-08 | STA-FGS Alignment Matrix Update 3 (for GA Boresight Shift) | 51.4462 | day | 1.54 | hr | 51.5104 | day
| 178 | OTE-08 | STA-FGS Alignment Matrix Update 3 (for GA Boresight Shift) - Analysis | 51.5104 | day | 5.75 | hr | 51.75 | day
| 194 | OTE-09 | Image Stacking 1 | 51.75 | day | 12.5 | hr | 52.2708 | day
| 194 | OTE-09 | Image Stacking 1 - Analysis | 52.2708 | day | 45 | hr | 54.1458 | day
| 899.5 | NRC-35 | NIRCam Ice Measurement | 53.61 | day | 1.15 | hr | 53.6579 | day
| 773.1 | NRC-04 | NIRCam Short Wave Pupil Wheel Tuning (Initial FAM check) | 54.1458 | day | 2.325 | hr | 54.2427 | day
| 773.1 | NRC-04 | NIRCam Short Wave Pupil Wheel Tuning (Initial FAM check) - Analysis | 54.2427 | day | 3 | hr | 54.3677 | day
| 773.2 | NRC-04 | NIRCam Short Wave Pupil Wheel Tuning (FAM Adjustment) | 54.3677 | day | 2.43 | hr | 54.469 | day
| 773.2 | NRC-04 | NIRCam Short Wave Pupil Wheel Tuning (FAM Adjustment) - Analysis | 54.469 | day | 4 | hr | 54.6356 | day
| 35 |  | Disable Autonomous On-board Control of IRSU CCH Zone 5 | 54.55 | day | 0.52 | hr | 54.5717 | day
| 855 |  | Re-Enable IRSU CCH Zone 5 | 54.5717 | day | 0.35 | hr | 54.5862 | day
| 851 |  | IRSU FM Overcurrent Limit Adjustment | 54.5862 | day | 0.33 | hr | 54.6 | day
| 181.1 | OTE-10 | SIAF PRD and Onboard Updates for NIRCam and FGS | 54.6356 | day | 4.55 | hr | 54.8252 | day
| 181.1 | OTE-10 | SIAF PRD and Onboard Updates for NIRCam and FGS - Analysis | 54.8252 | day | 43 | hr | 56.6169 | day
| 853 | OTE-11 | SIAF PRD Update for NIRISS | 54.8252 | day | 2.7 | hr | 54.9377 | day
| 853 | OTE-11 | SIAF PRD Update for NIRISS - Analysis | 54.9377 | day | 39 | hr | 56.5627 | day
| 773.3 | NRC-04 | NIRCam Short Wave Pupil Wheel Tuning (SW PW Alignment Check) | 54.9377 | day | 8.43 | hr | 55.289 | day
| 773.3 | NRC-04 | NIRCam Short Wave Pupil Wheel Tuning (SW PW Alignment Check) - Analysis | 55.289 | day | 7 | hr | 55.5806 | day
| 776 |  | Enable IRSU Master Trim Heater Control | 55.289 | day | 0.22 | hr | 55.2981 | day
| 779 |  | Set IRSU Trim Heater Power for NIRSpec FPA | 55.2981 | day | 0.22 | hr | 55.3073 | day
| 773.4 | NRC-04 | NIRCam Short Wave Pupil Wheel Tuning (WLP4 Alignment Check) | 55.5806 | day | 2.9 | hr | 55.7015 | day
| 773.4 | NRC-04 | NIRCam Short Wave Pupil Wheel Tuning (WLP4 Alignment Check) - analysis | 55.7015 | day | 2 | hr | 55.7848 | day
| 773.5 | NRC-04 | NIRCam Short Wave Pupil Wheel Tuning (Final Alignment Checks) | 55.7848 | day | 3.52 | hr | 55.9315 | day
| 773.5 | NRC-04 | NIRCam Short Wave Pupil Wheel Tuning (Final Alignment Checks) - analysis | 55.9315 | day | 5 | hr | 56.1398 | day
| 370 |  | IRU Calibration 2 | 55.9315 | day | 4 | hr | 56.0981 | day
| 370 |  | IRU Calibration 2 - Analysis | 56.0981 | day | 5 | hr | 56.3065 | day
| 762 | NRS-40 | NIRSpec FPA Heater Control | 56.2981 | day | 0.23 | hr | 56.3077 | day
| 222.1 | NRS-03 | NIRSpec SCA+ASIC Tuning Verification | 56.3077 | day | 1.82 | hr | 56.3835 | day
| 181.2 | OTE-10 | SIAF PRD and Onboard Updates for NIRCam and FGS | 56.6169 | day | 2.23 | hr | 56.7098 | day
| 181.2 | OTE-10 | SIAF PRD and Onboard Updates for NIRCam and FGS - Analysis | 56.7098 | day | 1 | hr | 56.7515 | day
| 899.6 | NRC-35 | NIRCam Ice Measurement | 56.7098 | day | 1.15 | hr | 56.7577 | day
| 60 | NRC-05 | NIRCam Pre-Coarse Phasing Verification | 56.7577 | day | 11.38 | hr | 57.2319 | day
| 60 | NRC-05 | NIRCam Pre-Coarse Phasing Verification - Analysis | 57.2319 | day | 12.5 | hr | 57.7527 | day
| 853.2 | OTE-11 | SIAF PRD Update for NIRISS | 57.2319 | day | 1.16 | hr | 57.2802 | day
| 853.2 | OTE-11 | SIAF PRD Update for NIRISS - Analysis | 57.2802 | day | 1 | hr | 57.3219 | day
| 137 | NRS-12 | NIRSpec ICE Initialization and Calibration Assembly Checkout | 57.2802 | day | 1.72 | hr | 57.3519 | day
| 106 | NRS-28 | NIRSpec FWA checkout | 57.3519 | day | 8.3 | hr | 57.6977 | day
| 223 | NRS-09 | NIRSpec RMA Checkout and Move to Mid-Position | 57.6977 | day | 0.5 | hr | 57.7185 | day
| 766 | NRS-10 | NIRSpec RMA Characterization | 57.7185 | day | 0.59 | hr | 57.7431 | day
| 107 | NRS-29 | NIRSpec GWA checkout | 57.7431 | day | 2.58 | hr | 57.8506 | day
| 157 | OTE-12 | Coarse Phasing 1 | 57.8507 | day | 8.48 | hr | 58.204 | day
| 157 | OTE-12 | Coarse Phasing 1 - Analysis | 58.204 | day | 11.5 | hr | 58.6832 | day
| 159 | NRS-14 | NIRSpec MSA Electrical Shorts Detection | 58.204 | day | 3.89 | hr | 58.3661 | day
| 159 | NRS-14 | NIRSpec MSA Electrical Shorts Detection - Ground Analysis | 58.3661 | day | 37 | hr | 59.9078 | day
| 156 | OTE-13 | NIRCam-only Coarse MIMF | 58.6832 | day | 24.97 | hr | 59.7236 | day
| 156 | OTE-13 | NIRCam-only Coarse MIMF - Analysis | 59.7236 | day | 73.5 | hr | 62.7861 | day
| 881 | NRS-43 | NIRSpec MSA Optical Shorts Identification and Masking | 59.9078 | day | 2.53 | hr | 60.0132 | day
| 881 | NRS-43 | NIRSpec MSA Optical Shorts Identification and Masking - Analysis | 60.0132 | day | 48 | hr | 62.0132 | day
| 152 | NRS-15 | NIRSpec MSA Performance and Geometry Characterization | 62.0132 | day | 4.28 | hr | 62.1915 | day
| 887.2 | MIR-42.6 | End MIRI POM Cooldown Operations | 62.1915 | day | 0.25 | hr | 62.202 | day
| 222.2 | NRS-03 | NIRSpec SCA+ASIC Tuning Verification | 62.202 | day | 1.62 | hr | 62.2695 | day
| 96.1 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 62.2695 | day | 4.83 | hr | 62.4707 | day
| 96.2 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 62.4707 | day | 4.83 | hr | 62.672 | day
| 179 | OTE-14 | STA-FGS Alignment Matrix Update 4 (for Coarse MIMF) | 62.7861 | day | 1.43 | hr | 62.8457 | day
| 179 | OTE-14 | STA-FGS Alignment Matrix Update 4 (for Coarse MIMF) - Analysis | 62.8457 | day | 5.5 | hr | 63.0749 | day
| 170.3 |  | Momentum Unload (if needed) | 62.9057 | day | 3.48 | hr | 63.0507 | day
| 188 | OTE-15.1 | Segment Image Array 2 | 63.0749 | day | 2.617 | hr | 63.1839 | day
| 188 | OTE-15.1 | Segment Image Array 2 - Analysis | 63.1839 | day | 10 | hr | 63.6006 | day
| 96.3 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 63.1839 | day | 4.83 | hr | 63.3852 | day
| 96.4 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 63.3852 | day | 4.83 | hr | 63.5864 | day
| 185 | OTE-16.1 | Global Alignment 2 | 63.6006 | day | 13.56 | hr | 64.1656 | day
| 185 | OTE-16.1 | Global Alignment 2 - Analysis | 64.1656 | day | 35 | hr | 65.6239 | day
| 96.5 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 64.1656 | day | 3.42 | hr | 64.3081 | day
| 96.6 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 64.3081 | day | 4.833 | hr | 64.5095 | day
| 96.7 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 64.5095 | day | 4.83 | hr | 64.7107 | day
| 96.8 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 64.7107 | day | 4.83 | hr | 64.912 | day
| 96.9 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 64.912 | day | 4.83 | hr | 65.1132 | day
| 96.10 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 65.1132 | day | 3.43 | hr | 65.2561 | day
| 173 | OTE-17.1 | Image Stacking 2 | 65.6239 | day | 3.24 | hr | 65.7589 | day
| 173 | OTE-17.1 | Image Stacking 2 - Analysis | 65.7589 | day | 6 | hr | 66.0089 | day
| 96.11 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 65.7589 | day | 4.83 | hr | 65.9602 | day
| 67 | OTE-18.1 | Fine Phasing 1 | 66.0089 | day | 11.55 | hr | 66.4902 | day
| 67 | OTE-18.1 | Fine Phasing 1 - Analysis | 66.4902 | day | 17 | hr | 67.1985 | day
| 96.12 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 66.4902 | day | 4.83 | hr | 66.6914 | day
| 96.13 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 66.6914 | day | 4.83 | hr | 66.8927 | day
| 899.7 | NRC-35 | NIRCam Ice Measurement | 66.8927 | day | 1.15 | hr | 66.9406 | day
| 186 | OTE-19.1 | Coarse Phasing 2 | 67.1985 | day | 5.33 | hr | 67.4206 | day
| 186 | OTE-19.1 | Coarse Phasing 2 - Analysis | 67.4206 | day | 8.5 | hr | 67.7747 | day
| 96.14 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 67.4206 | day | 4.83 | hr | 67.6218 | day
| 96.15 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 67.6218 | day | 3.42 | hr | 67.7643 | day
| 189 | OTE-21.1 | Fine Phasing 2 | 67.7747 | day | 11.93 | hr | 68.2718 | day
| 189 | OTE-21.1 | Fine Phasing 2 - Analysis | 68.2718 | day | 21 | hr | 69.1468 | day
| 96.16 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 68.2718 | day | 4.83 | hr | 68.4731 | day
| 96.17 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 68.4731 | day | 4.83 | hr | 68.6743 | day
| 96.18 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 68.6743 | day | 4.83 | hr | 68.8756 | day
| 190 | OTE-22.1 | Coarse Phasing 3 | 69.1468 | day | 8.07 | hr | 69.4831 | day
| 190 | OTE-22.1 | Coarse Phasing 3 - Analysis | 69.4831 | day | 10 | hr | 69.8998 | day
| 96.19 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 69.4831 | day | 4.83 | hr | 69.6843 | day
| 862.2 |  | Stationkeeping maneuver | 69.6843 | day | 3.3333 | hr | 69.8232 | day
| 191 | OTE-23.1 | Fine Phasing 3 | 69.8998 | day | 8.65 | hr | 70.2602 | day
| 191 | OTE-23.1 | Fine Phasing 3 - Analysis | 70.2602 | day | 10.17 | hr | 70.6839 | day
| 96.20 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 70.2602 | day | 3.42 | hr | 70.4027 | day
| 192.1 | OTE-25.1 | NIRCam Multi-Field Monitor | 70.6839 | day | 13.73 | hr | 71.256 | day
| 269.1 | OTE-27 | SIAF PRD Update for NIRSpec | 71.256 | day | 3.9 | hr | 71.4185 | day
| 269.1 | OTE-27 | SIAF PRD Update for NIRSpec - Analysis | 71.4185 | day | 39 | hr | 73.0435 | day
| 903.2 |  | OTE FSM Stablity and Spiral Scan | 71.4185 | day | 1.95 | hr | 71.4998 | day
| 96.21 | NRS-21 | NIRSpec Full Frame Darks and Super-Bias | 71.4998 | day | 21.63 | hr | 72.401 | day
| 102.1 | NRC-09 | NIRCam Darks | 72.401 | day | 0.7 | hr | 72.4302 | day
| 269.2 | OTE-27 | SIAF PRD Update for NIRSpec | 73.0435 | day | 1.41 | hr | 73.1023 | day
| 269.2 | OTE-27 | SIAF PRD Update for NIRSpec - Analysis | 73.1023 | day | 1 | hr | 73.1439 | day
| 193 | OTE-28.1 | Pre-MIMF In-Focus PSF Check | 73.1439 | day | 6.47 | hr | 73.4135 | day
| 193 | OTE-28.1 | Pre-MIMF In-Focus PSF Check - Analysis | 73.4135 | day | 30 | hr | 74.6635 | day
| 71.1 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 73.416 | day | 2.08 | hr | 73.5027 | day
| 71.1 | OTE-26 | WFSC Routine/CC Jitter Maintenance - Analysis | 73.5027 | day | 2 | hr | 73.586 | day
| 801 | FGS-06 | Medium Angle Maneuvers | 73.586 | day | 2.58 | hr | 73.6935 | day
| 759 | FGS-19 | Fuel Slosh LOS Characterization | 73.6935 | day | 5.45 | hr | 73.9206 | day
| 170.4 |  | Momentum Unload | 74.5185 | day | 3.48 | hr | 74.6635 | day
| 925 |  | MRE Calibration and CG Estimation (in parallel with MU) | 74.5185 | day | 3.48 | hr | 74.6635 | day
| 68 | OTE-29.1 | MIMF Measurement 1 | 74.6635 | day | 39.4 | hr | 76.3052 | day
| 68 | OTE-29.1 | MIMF Measurement 1 - Analysis | 76.3052 | day | 52 | hr | 78.4718 | day
| 899.8 | NRC-35 | NIRCam Ice Measurement (w/ NIRSpec) - Pre transition to state 4 | 77 | day | 1.57 | hr | 77.0654 | day
| 899.8 | NRC-35 | NIRCam Ice Measurement - Ground Analysis | 77.0654 | day | 10 | hr | 77.4821 | day
| 192.2 | OTE-25.2 | NIRCam Multi-Field Monitor | 77.0654 | day | 13.73 | hr | 77.6375 | day
| 133.1 |  | CAM for Cryocooler Transition to State 4 | 77.4821 | day | 1 | hr | 77.5238 | day
| 170.5 |  | Momentum Unload (if needed) | 77.5958 | day | 3.48 | hr | 77.7408 | day
| 803.1 | OTE-24 | Cryocooler Jitter Measurements (Pre State 4) | 77.7408 | day | 2.35 | hr | 77.8387 | day
| 133.1 |  | Cryocooler Transition to State 4 (JT Bypass Cooldown) | 77.8387 | day | 37.15 | hr | 79.3867 | day
| 803.2 | OTE-24 | Cryocooler Jitter Measurements (Post State 4) | 79.3867 | day | 13.27 | hr | 79.9396 | day
| 71.2 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 79.9475 | day | 2.08 | hr | 80.0342 | day
| 71.2 | OTE-26 | WFSC Routine/CC Jitter Maintenance - Analysis | 80.0342 | day | 2 | hr | 80.1175 | day
| 867.1 | NRC-16 | NIRCam Post-MIMF Focus Adjustment | 80.0418 | day | 2.37 | hr | 80.1406 | day
| 868.1 | NIS-32 | NIRISS Post-MIMF Focus Adjustment | 80.1406 | day | 1.2 | hr | 80.1906 | day
| 869.1 | NRS-20 | NIRSpec Post-MIMF Focus Adjustment | 80.1906 | day | 0.21 | hr | 80.1993 | day
| 870.1 | FGS-18 | FGS Post-MIMF Focus Adjustment | 80.1993 | day | 1.13 | hr | 80.2464 | day
| 356 | OTE-31.1 | MIMF Correction 1 | 80.2464 | day | 2.22 | hr | 80.3389 | day
| 356 | OTE-31.1 | MIMF Correction 1 - Analysis | 80.3389 | day | 2 | hr | 80.4223 | day
| 354 | OTE-32.1 | STA-FGS Alignment Matrix Update 5 (for MIMF Correction) | 80.4223 | day | 1.36 | hr | 80.4789 | day
| 354 | OTE-32.1 | STA-FGS Alignment Matrix Update 5 (for MIMF Correction) - Analysis | 80.4789 | day | 5.5 | hr | 80.7081 | day
| 900 |  | Set IRSU Trim Heater Power for NIRSpec OA | 80.53 | day | 0.22 | hr | 80.5392 | day
| 69.1 | OTE-15.2 | MIMF Recovery 1: Segment Image Array 3 | 80.7081 | day | 2.617 | hr | 80.8171 | day
| 69.1 | OTE-15.2 | MIMF Recovery 1: Segment Image Array 3 - Analysis | 80.8171 | day | 8.83 | hr | 81.185 | day
| 778 |  | Set IRSU Trim Heater Power for NIRCam OA | 80.87 | day | 0.22 | hr | 80.8792 | day
| 69.2 | OTE-16.2 | MIMF Recovery 1: Global Alignment 2 | 81.185 | day | 13.56 | hr | 81.75 | day
| 69.2 | OTE-16.2 | MIMF Recovery 1: Global Alignment 2 - Analysis | 81.75 | day | 35 | hr | 83.2084 | day
| 785.1 | NRC-06 | NIRCam FPA Temperature Control | 81.8 | day | 0.55 | hr | 81.8229 | day
| 69.3 | OTE-17.2 | MIMF Recovery 1: Image Stacking 3 | 83.2084 | day | 3.24 | hr | 83.3434 | day
| 69.3 | OTE-17.2 | MIMF Recovery 1: Image Stacking 3 - Analysis | 83.3434 | day | 6 | hr | 83.5934 | day
| 785.2 | NRC-06 | NIRCam FPA Temperature Control | 84 | day | 0.45 | hr | 84.0187 | day
| 767 | NRS-41 | NIRSpec Instrument Model Verification and GWA Tilt Sensor Calibration | 84.96 | day | 20 | hr | 85.7933 | day
| 767 | NRS-41 | NIRSpec Instrument Model Verification and GWA Tilt Sensor Calibration - Analysis | 85.7933 | day | 72 | hr | 88.7933 | day
| 69.4 | OTE-18.2 | MIMF Recovery 1: Fine Phasing 4 | 85.8867 | day | 11.55 | hr | 86.3679 | day
| 69.4 | OTE-18.2 | MIMF Recovery 1: Fine Phasing 4 - Analysis | 86.3679 | day | 14 | hr | 86.9512 | day
| 108.1 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 86.3679 | day | 4.39 | hr | 86.5508 | day
| 108.2 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 86.5508 | day | 3.73 | hr | 86.7062 | day
| 859 | MIR-42.7 | MIRI FPM Heater 2nd Adjustment | 86.7062 | day | 0.39 | hr | 86.7225 | day
| 108.3 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 86.7225 | day | 4.25 | hr | 86.8996 | day
| 69.5 | OTE-19.2 | MIMF Recovery 1: Coarse Phasing 4 | 86.9512 | day | 5.325 | hr | 87.1731 | day
| 69.5 | OTE-19.2 | MIMF Recovery 1: Coarse Phasing 4 - Analysis | 87.1731 | day | 8.5 | hr | 87.5273 | day
| 102.2 | NRC-09 | NIRCam Darks | 87.1731 | day | 4.917 | hr | 87.378 | day
| 102.3 | NRC-09 | NIRCam Darks | 87.378 | day | 4.175 | hr | 87.552 | day
| 69.6 | OTE-21.2 | MIMF Recovery 1: Fine Phasing 5 | 87.5553 | day | 11.925 | hr | 88.0522 | day
| 69.6 | OTE-21.2 | MIMF Recovery 1: Fine Phasing 5 - Analysis | 88.0522 | day | 20 | hr | 88.8855 | day
| 108.4 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 88.0522 | day | 3.73 | hr | 88.2076 | day
| 108.5 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 88.2076 | day | 4.392 | hr | 88.3906 | day
| 108.6 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 88.3906 | day | 4.86 | hr | 88.5931 | day
| 777 |  | IRSU Trim Heater Enable - FGS & NIRISS | 88.5931 | day | 0.22 | hr | 88.6023 | day
| 102.4 | NRC-09 | NIRCam Darks | 88.6023 | day | 5.16 | hr | 88.8173 | day
| 69.7 | OTE-22.2 | MIMF Recovery 1: Coarse Phasing 5 | 88.8855 | day | 7.233 | hr | 89.1869 | day
| 69.7 | OTE-22.2 | MIMF Recovery 1: Coarse Phasing 5 - Analysis | 89.1869 | day | 10 | hr | 89.6035 | day
| 108.7 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 89.1869 | day | 4.39 | hr | 89.3698 | day
| 108.8 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 89.3698 | day | 4.25 | hr | 89.5469 | day
| 757 | NIS-24 | NIRISS FPA Heater ON | 89.5523 | day | 0.4 | hr | 89.5689 | day
| 69.8 | OTE-23.2 | MIMF Recovery 1: Fine Phasing 6 | 89.6035 | day | 6.98 | hr | 89.8944 | day
| 69.8 | OTE-23.2 | MIMF Recovery 1: Fine Phasing 6 - Analysis | 89.8944 | day | 10 | hr | 90.311 | day
| 345.1 | NIS-06 | NIRISS Darks | 89.8944 | day | 4.81 | hr | 90.0948 | day
| 345.1 | NIS-06 | NIRISS Darks - Analysis | 90.0948 | day | 24 | hr | 91.0948 | day
| 860 | MIR-42.8 | MIRI FPM Heater 3rd Adjustment | 90.0948 | day | 0.43 | hr | 90.1127 | day
| 862.3 |  | Stationkeeping maneuver | 90.1127 | day | 3.33 | hr | 90.2515 | day
| 69.9 | OTE-25.3 | MIMF Recovery 1: NIRCam Multi-Field Monitor 3 | 90.311 | day | 13.733 | hr | 90.8833 | day
| 108.9 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 90.8833 | day | 3.73 | hr | 91.0387 | day
| 345.2 | NIS-06 | NIRISS Darks | 91.0387 | day | 12.58 | hr | 91.5628 | day
| 102.5 | NRC-09 | NIRCam Darks | 91.5628 | day | 5.16 | hr | 91.7778 | day
| 763.1 | NRS-39 | NIRSpec Subarray Darks and Super-Bias | 91.7778 | day | 15.325 | hr | 92.4164 | day
| 345.3 | NIS-06 | NIRISS Darks | 92.4164 | day | 12.58 | hr | 92.9405 | day
| 818 | MIR-42.9 | MIRI FPM Heater Power OFF | 92.43 | day | 0.33 | hr | 92.4438 | day
| 133.2 |  | Cryocooler (CCE) Transition to State 4 (JT Bypass Cooldown) | 92.4438 | day | 0.45 | hr | 92.4625 | day
| 71.3 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 92.9433 | day | 2.13 | hr | 93.032 | day
| 71.3 | OTE-26 | WFSC Routine/CC Jitter Maintenance - Analysis | 93.032 | day | 2 | hr | 93.1153 | day
| 102.6 | NRC-09 | NIRCam Darks | 93.1153 | day | 3.84 | hr | 93.2753 | day
| 134.1 |  | Cryocooler Transition to State 5 (Pinch Point) | 93.28 | day | 18.15 | hr | 94.0362 | day
| 768 | NRS-24 | NIRSpec Internal Subarray Flat Fields | 94.0362 | day | 2.375 | hr | 94.1352 | day
| 764.3 | MIR-71 | MIRI ICE Basic Functional Test | 94.1604 | day | 1.02 | hr | 94.2029 | day
| 117 | MIR-40 | MIRI Mechanism Characterization | 94.2029 | day | 27.4 | hr | 95.3446 | day
| 71.4 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 95.352 | day | 2.13 | hr | 95.4408 | day
| 71.4 | OTE-26 | WFSC Routine/CC Jitter Maintenance - Analysis | 95.4408 | day | 2 | hr | 95.5241 | day
| 118 | MIR-41 | MIRI Pick-Off Mirror Characterization | 95.4408 | day | 0.93 | hr | 95.4795 | day
| 118 | MIR-41 | MIRI Pick-Off Mirror Characterization - Analysis | 95.4795 | day | 3 | hr | 95.6045 | day
| 102.7 | NRC-09 | NIRCam Darks | 95.4795 | day | 3.86 | hr | 95.6403 | day
| 134.2 |  | Cryocooler Transition to State 5 (Pinch Point) | 95.6445 | day | 4.61 | hr | 95.8366 | day
| 126 | MIR-02 | MIRI Focal Plane System Cold Checkout | 95.7145 | day | 2.9 | hr | 95.8353 | day
| 74.1 | MIR-05 | MIRI Detector Anneal (First Instance) | 95.8353 | day | 6.16 | hr | 96.092 | day
| 136 |  | Cryocooler Transition to State 6 (Steady State) | 96.092 | day | 0.75 | hr | 96.1232 | day
| 136 |  | Cryocooler Transition to State 6 (Steady State) - dwell | 96.1232 | day | 15 | hr | 96.7482 | day
| 763.2 | NRS-39 | NIRSpec Subarray Darks and Super-Bias | 96.2632 | day | 3.29 | hr | 96.4003 | day
| 108.10 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 96.4003 | day | 7.842 | hr | 96.7271 | day
| 73 | MIR-04 | MIRI Calibration Lamp Operation | 96.7482 | day | 3.48 | hr | 96.8932 | day
| 74.2 | MIR-05 | MIRI Detector Anneal | 96.8932 | day | 3.78 | hr | 97.0507 | day
| 71.5 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 97.0518 | day | 2.13 | hr | 97.1405 | day
| 71.5 | OTE-26 | WFSC Routine/CC Jitter Maintenance - Analysis | 97.1405 | day | 2 | hr | 97.2238 | day
| 115 | MIR-14 | MIRI Read Noise and Dark Current | 97.1405 | day | 2.133 | hr | 97.2294 | day
| 924.1 | MIR-65 | FPS Frame Resets and RSCD Characterization | 97.2294 | day | 3.09 | hr | 97.3581 | day
| 924.1 | MIR-65 | FPS Frame Resets and RSCD Characterization -analysis | 97.3581 | day | 4 | hr | 97.5248 | day
| 170.6 |  | Momentum Unload | 97.3581 | day | 3.48 | hr | 97.5031 | day
| 804 | OTE-33 | Cryocooler Jitter Measurements 2: Image Motion Assessment | 97.5031 | day | 1.35 | hr | 97.5594 | day
| 804 | OTE-33 | Cryocooler Jitter Measurements 2: Image Motion Assessment - analysis | 97.5594 | day | 4 | hr | 97.726 | day
| 924.2 | MIR-65 | FPS Frame Resets and RSCD Characterization | 97.5594 | day | 3.09 | hr | 97.6881 | day
| 924.2 | MIR-65 | FPS Frame Resets and RSCD Characterization -analysis | 97.6881 | day | 4 | hr | 97.8548 | day
| 805 | OTE-33 | Cryo-Cooler Jitter Measurements 2: Frequency Sweep | 97.726 | day | 3.22 | hr | 97.8602 | day
| 805 | OTE-33 | Cryo-Cooler Jitter Measurements 2: Frequency Sweep - analysis | 97.8602 | day | 4 | hr | 98.0269 | day
| 899.9 | NRC-35 | NIRCam Ice Measurement (w/ NIRSpec) | 97.8602 | day | 1.57 | hr | 97.9256 | day
| 763.3 | NRS-39 | NIRSpec Subarray Darks and Super-Bias | 97.9256 | day | 3.29 | hr | 98.0627 | day
| 805 | OTE-33 | Cryo-Cooler Jitter Measurements 2: Frequency Sweep Commanding | 98.058 | day | 0.33 | hr | 98.0717 | day
| 139 | MIR-60 | MIRI Detector Functionality | 98.0717 | day | 4.142 | hr | 98.2443 | day
| 74.3 | MIR-05 | MIRI Detector Anneals | 98.2443 | day | 1.46 | hr | 98.3051 | day
| 765 |  | MIRI CCC Opening 2 | 98.3051 | day | 0.3 | hr | 98.3176 | day
| 270.1 | OTE-34 | SIAF PRD Update for MIRI | 98.3176 | day | 3.94 | hr | 98.4818 | day
| 270.1 | OTE-34 | SIAF PRD Update for MIRI - Analysis | 98.4818 | day | 39 | hr | 100.1068 | day
| 904 | MIRI-80 | MIRI JT Assisted Anneal Recovery | 98.4818 | day | 3.325 | hr | 98.6204 | day
| 345.4 | NIS-06 | NIRISS Darks | 98.6204 | day | 15.05 | hr | 99.2474 | day
| 71.6 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 99.2505 | day | 2.13 | hr | 99.3393 | day
| 71.6 | OTE-26 | WFSC Routine/CC Jitter Maintenance - Analysis | 99.3393 | day | 2 | hr | 99.4226 | day
| 102.8 | NRC-09 | NIRCam Darks | 99.3393 | day | 1.18 | hr | 99.3884 | day
| 763.4 | NRS-39 | NIRSpec Subarray Darks and Super-Bias | 99.3884 | day | 4.975 | hr | 99.5957 | day
| 108.11 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 99.5957 | day | 4.86 | hr | 99.7982 | day
| 102.9 | NRC-09 | NIRCam Darks | 99.7982 | day | 1.18 | hr | 99.8474 | day
| 345.5 | NIS-06 | NIRISS Darks | 99.8474 | day | 4.996 | hr | 100.0555 | day
| 270.2 | OTE-34 | SIAF PRD Update for MIRI | 100.1068 | day | 1.158 | hr | 100.1551 | day
| 69.10 | OTE-28.2 | MIMF Recovery 1: Pre-MIMF In-Focus PSF Check 2 | 100.1967 | day | 9.92 | hr | 100.6101 | day
| 69.10 | OTE-28.2 | MIMF Recovery 1: Pre-MIMF In-Focus PSF Check 2 - Analysis | 100.6101 | day | 30 | hr | 101.8601 | day
| 352 | OTE-35 | MIRI Pupil Alignment Check | 100.6101 | day | 0.95 | hr | 100.6496 | day
| 352 | OTE-35 | MIRI Pupil Alignment Check - Analysis | 100.6496 | day | 10 | hr | 101.0663 | day
| 345.6 | NIS-06 | NIRISS Darks | 100.6496 | day | 5.4 | hr | 100.8746 | day
| 71.7 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 101.0693 | day | 2.13 | hr | 101.158 | day
| 71.7 | OTE-26 | WFSC Routine/CC Jitter Maintenance - Analysis | 101.158 | day | 2 | hr | 101.2413 | day
| 346 | NIS-07 | NIRISS Calibration Lamps Verification | 101.158 | day | 2.28 | hr | 101.253 | day
| 347 | NIS-08 | NIRISS Internal Flat Fields | 101.253 | day | 4.08 | hr | 101.423 | day
| 97 | FGS-10 | FGS-Guider Internal Lamp Flat Field | 101.423 | day | 6.87 | hr | 101.7093 | day
| 170.7 |  | Momentum Unload (if needed) | 101.7093 | day | 3.48 | hr | 101.8543 | day
| 84 | OTE-29.2 | MIMF Measurement 2 | 101.8601 | day | 45.68 | hr | 103.7634 | day
| 84 | OTE-29.2 | MIMF Measurement 2 - Analysis | 103.7634 | day | 48 | hr | 105.7634 | day
| 192.3 | OTE-25.4 | NIRCam Multi-Field Monitor 4 | 103.7634 | day | 13.733 | hr | 104.3356 | day
| 763.6 | NRS-39 | NIRSpec Subarray Darks and Super-Bias | 104.3356 | day | 16.6 | hr | 105.0273 | day
| 108.12 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 105.0273 | day | 3.733 | hr | 105.1828 | day
| 348 | NIS-09 | NIRISS Detector Gain | 105.1828 | day | 3.12 | hr | 105.3128 | day
| 102.10 | NRC-09 | NIRCam Darks | 105.3128 | day | 1.18 | hr | 105.362 | day
| 867.2 | NRC-16 | NIRCam Post-MIMF Focus Adjustment | 105.7634 | day | 2.37 | hr | 105.8621 | day
| 868.2 | NIS-32 | NIRISS Post-MIMF Focus Adjustment | 105.8621 | day | 1.2 | hr | 105.9121 | day
| 869.2 | NRS-20 | NIRSpec Post-MIMF Focus Adjustment | 105.9121 | day | 0.21 | hr | 105.9209 | day
| 870.2 | FGS-18 | FGS Post-MIMF Focus Adjustment | 105.9209 | day | 1.13 | hr | 105.968 | day
| 749 | OTE-31.2 | MIMF Correction 2 | 105.968 | day | 2.19 | hr | 106.0592 | day
| 749 | OTE-31.2 | MIMF Correction 2 - Analysis | 106.0592 | day | 2 | hr | 106.1426 | day
| 108.13 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 106.0592 | day | 4.392 | hr | 106.2422 | day
| 750 | OTE-32.2 | STA-FGS Alignment Matrix Update 6 (for MIMF Correction) | 106.1426 | day | 6.85 | hr | 106.428 | day
| 751.1 | OTE-15.3 | MIMF Recovery 2: Segment Image Array 4 | 106.428 | day | 2.617 | hr | 106.537 | day
| 751.1 | OTE-15.3 | MIMF Recovery 2: Segment Image Array 4 - Analysis | 106.537 | day | 8.83 | hr | 106.9049 | day
| 108.14 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 106.537 | day | 4.25 | hr | 106.7141 | day
| 108.15 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 106.7141 | day | 4.39 | hr | 106.897 | day
| 751.2 | OTE-16.3 | MIMF Recovery 2: Global Alignment 4 | 106.9049 | day | 13.55 | hr | 107.4695 | day
| 751.2 | OTE-16.3 | MIMF Recovery 2: Global Alignment 4 - Analysis | 107.4695 | day | 35 | hr | 108.9279 | day
| 763.5 | NRS-39 | NIRSpec Subarray Darks and Super-Bias | 107.4695 | day | 10.43 | hr | 107.9041 | day
| 108.16 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 107.9041 | day | 3.733 | hr | 108.0596 | day
| 108.17 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 108.0596 | day | 4.858 | hr | 108.2621 | day
| 108.18 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 108.2621 | day | 4.39 | hr | 108.445 | day
| 108.19 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 108.445 | day | 3.73 | hr | 108.6004 | day
| 108.20 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 108.6004 | day | 4.25 | hr | 108.7775 | day
| 751.3 | OTE-17.3 | MIMF Recovery 2: Image Stacking 4 | 108.9279 | day | 3.242 | hr | 109.0629 | day
| 751.3 | OTE-17.3 | MIMF Recovery 2: Image Stacking 4 - Analysis | 109.0629 | day | 6 | hr | 109.3129 | day
| 108.21 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 109.0629 | day | 4.39 | hr | 109.2459 | day
| 751.4 | OTE-18.3 | MIMF Recovery 2: Fine Phasing 7 | 109.3129 | day | 11.55 | hr | 109.7942 | day
| 751.4 | OTE-18.3 | MIMF Recovery 2: Fine Phasing 7 - Analysis | 109.7942 | day | 17 | hr | 110.5025 | day
| 108.22 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 109.7942 | day | 4.86 | hr | 109.9967 | day
| 108.23 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 109.9967 | day | 3.73 | hr | 110.1521 | day
| 108.24 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 110.1521 | day | 3.73 | hr | 110.3075 | day
| 751.5 | OTE-19.3 | MIMF Recovery 2: Coarse Phasing 6 | 110.5025 | day | 5.33 | hr | 110.7246 | day
| 751.5 | OTE-19.3 | MIMF Recovery 2: Coarse Phasing 6 - Analysis | 110.7246 | day | 8.5 | hr | 111.0788 | day
| 108.25 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 110.7246 | day | 4.39 | hr | 110.9075 | day
| 862.4 |  | Stationkeeping maneuver | 110.9075 | day | 3.3333 | hr | 111.0464 | day
| 751.6 | OTE-21.3 | MIMF Recovery 2: Fine Phasing 8 | 111.0788 | day | 11.925 | hr | 111.5756 | day
| 751.6 | OTE-21.3 | MIMF Recovery 2: Fine Phasing 8 - Analysis | 111.5756 | day | 21 | hr | 112.4506 | day
| 108.26 | NRS-22 | NIRSpec MSA Internal Spectral Flatfield and Wavelength Calibration | 111.5756 | day | 4.25 | hr | 111.7527 | day
| 751.7 | OTE-22.3 | MIMF Recovery 2: Coarse Phasing 7 | 112.4506 | day | 7.233 | hr | 112.752 | day
| 751.7 | OTE-22.3 | MIMF Recovery 2: Coarse Phasing 7 - Analysis | 112.752 | day | 10 | hr | 113.1687 | day
| 751.8 | OTE-23.3 | MIMF Recovery 2: Fine Phasing 9 | 113.1687 | day | 6.983 | hr | 113.4596 | day
| 751.8 | OTE-23.3 | MIMF Recovery 2: Fine Phasing 9 - Analysis | 113.4596 | day | 10 | hr | 113.8763 | day
| 751.9 | OTE-25.5 | MIMF Recovery 2: NIRCam Multi-Field Monitor 5 | 113.8763 | day | 13.733 | hr | 114.4485 | day
| 751.10 | OTE-28.3 | MIMF Recovery 2: Pre-MIMF In-Focus PSF Check 3 | 114.4485 | day | 9.292 | hr | 114.8357 | day
| 751.10 | OTE-28.3 | MIMF Recovery 2: Pre-MIMF In-Focus PSF Check 3 - Analysis | 114.8357 | day | 6 | hr | 115.0857 | day
| MILESTONE |  | MIMF Recovery Complete | 115.0857 | day | 0 | hr | 115.0857 | day
| 70 | OTE-29.3 | MIMF Measurement 3 | 115.0857 | day | 45.68 | hr | 116.989 | day
| 70 | OTE-29.3 | MIMF Measurement 3 - Analysis | 116.989 | day | 13 | hr | 117.5307 | day
| MILESTONE |  | OTE Alignment Complete | 117.5307 | day | 0.001 | hr | 117.5307 | day
| 373.1 | NIS-10.1 | NIRISS CFM Focus Sweep (Measure -1) | 118 | day | 1.8 | hr | 118.075 | day
| 373.1 | NIS-10.1 | NIRISS CFM Focus Sweep Ground Analysis | 118.075 | day | 72 | hr | 121.075 | day
| 104.1 | NRC-15 | NIRCam Focus Adjust - Collect data on Module 1 | 118.1583 | day | 3.25 | hr | 118.2938 | day
| 104.1 | NRC-15 | NIRCam Focus Adjust - Module 1 - Ground Analysis | 118.2938 | day | 3 | hr | 118.4188 | day
| 104.2 | NRC-15 | NIRCam Focus Adjust - Collect data on Module 2 | 118.3338 | day | 3.25 | hr | 118.4692 | day
| 104.2 | NRC-15 | NIRCam Focus Adjust - Module 2 - Ground Analysis | 118.4692 | day | 8 | hr | 118.8025 | day
| 99 | FGS-12 | FGS-Guider Focus | 118.5525 | day | 4.72 | hr | 118.7492 | day
| 99 | FGS-12 | FGS-Guider Focus - Ground Analysis | 118.7492 | day | 168 | hr | 125.7492 | day
| 111.1 | NRS-18.1 | NIRSpec focus determination | 118.8325 | day | 1.4 | hr | 118.8908 | day
| 111.1 | NRS-18.1 | NIRSpec focus - Ground Analysis | 118.8908 | day | 72 | hr | 121.8908 | day
| 78 | NRC-21 | NIRCam Astrometric Calibration | 118.9125 | day | 6.36 | hr | 119.1775 | day
| 78 | NRC-21 | NIRCam Astrometric Calibration - Ground Analysis | 119.1775 | day | 240 | hr | 129.1775 | day
| 905 | MIR-81 | MIRI JT Anneal Jitter | 119.2608 | day | 2.5 | hr | 119.365 | day
| 905 | MIR-81 | MIRI JT Anneal Jitter - Analysis | 119.365 | day | 96 | hr | 123.365 | day
| 71.8 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 119.419 | day | 2.13 | hr | 119.5078 | day
| 782 | NRC-21b | NIRCam Coronographic Astrometric Calibration | 119.5911 | day | 12.8 | hr | 120.1244 | day
| 80 | NRC-23 | NIRCam Image-Quality Verification by Filter | 120.2078 | day | 3.87 | hr | 120.2911 | day
| 219.1 | NRC-32.1 | NIRCam LW Grism Baseline Characterization | 120.3744 | day | 17.5 | hr | 121.1036 | day
| 219.1 | NRC-32.1 | NIRCam LW Grism Baseline Characterization Observation 1 - Ground Analysis | 120.4544 | day | 24 | hr | 121.4544 | day
| 373.2 | NIS-10.2 | NIRISS CFM Focus Sweep (Measure -2) | 121.175 | day | 0.5 | hr | 121.1958 | day
| 373.3 | NIS-10.2 | NIRISS CFM Focus Sweep Ground Analysis | 121.1958 | day | 8 | hr | 121.5292 | day
| 71.9 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 121.3078 | day | 2.13 | hr | 121.3965 | day
| 219.2 | NRC-32.2 | NIRCam LW Grism Baseline Characterization | 121.4544 | day | 1.5 | hr | 121.5169 | day
| 373.4 | NIS-10.3 | NIRISS CFM Focus Sweep (Measure - 3) | 121.5292 | day | 11.75 | hr | 122.0187 | day
| 373.3 | NIS-10.3 | NIRISS CFM Focus Sweep Ground Analysis | 122.0187 | day | 72 | hr | 125.0187 | day
| 111.2 | NRS-18.2 | NIRSpec focus uplink | 122.1008 | day | 0.25 | hr | 122.1113 | day
| 112 | NRS-19 | NIRSpec astrometric calibration | 122.1946 | day | 2.25 | hr | 122.2883 | day
| 112 | NRS-19 | NIRSpec astrometric calibration Ground Analysis | 122.2883 | day | 120 | hr | 127.2883 | day
| 901 | NRC-33 | NIRCam LW Grism Stability | 122.3717 | day | 4.85 | hr | 122.5738 | day
| 906.1 | MIRI-82.1 | MIRI JT Anneal Final Configuration | 123.365 | day | 0.5 | hr | 123.3858 | day
| 906.2 | MIRI-82.2 | MIRI JT Anneal Final Configuration | 123.5317 | day | 0.5 | hr | 123.5525 | day
| 906.3 | MIRI-82.3 | MIRI JT Anneal Final Configuration | 123.6983 | day | 0.5 | hr | 123.7192 | day
| 906.4 | MIRI-82.4 | MIRI JT Anneal Final Configuration | 123.865 | day | 0.5 | hr | 123.8858 | day
| 906.5 | MIRI-82.5 | MIRI JT Anneal Final Configuration | 124.0317 | day | 0.5 | hr | 124.0525 | day
| 71.10 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 124.0965 | day | 2.13 | hr | 124.1853 | day
| 903.3 |  | OTE FSM Stability & Spiral Scan | 124.2686 | day | 2 | hr | 124.3519 | day
| 74.4 | MIRI-05.03 | MIRI Detector Anneals (to support MIR-07) | 125.0525 | day | 3 | hr | 125.1775 | day
| 76 | MIRI-07 | MIRI Plate Scale & Geometric Distort Measure | 125.1775 | day | 10.7 | hr | 125.6233 | day
| 76 | MIRI-07 | MIRI Plate Scale & Geometric Distort Measure - Ground Analysis | 125.6233 | day | 504 | hr | 146.6233 | day
| 374 | NIS-11 | NIRISS External Flat Fields | 125.6687 | day | 17.81 | hr | 126.4108 | day
| 374 | NIS-11 | NIRISS External Flat Fields Ground Analysis | 126.4108 | day | 96 | hr | 130.4108 | day
| 71.11 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 126.4753 | day | 2.13 | hr | 126.564 | day
| 98 | FGS-11 | FGS-Guider Geometric Distortion and Scale | 126.5992 | day | 2.85 | hr | 126.7179 | day
| 862.5 |  | Stationkeeping maneuver | 126.8013 | day | 3.33 | hr | 126.94 | day
| 170.8 |  | Momentum Unload | 126.94 | day | 3.5 | hr | 127.0858 | day
| MILESTONE |  | Slew & Remain at HOT Attitude (0 +/- 5 deg pitch) | 127.0858 | day | 128.73 | hr | 132.4496 | day
| 819.1 | THS-02 | Slew to Hot Attitude | 127.0858 | day | 1 | hr | 127.1275 | day
| 812.1 | MIR-73.1 | MIRI Sky background variation with telescope pointing (part 1) | 127.2108 | day | 4.5 | hr | 127.3983 | day
| 809 |  | SC Bus HDE TCL Characterization | 127.5858 | day | 4 | hr | 127.7525 | day
| 71.12 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 127.8233 | day | 2.13 | hr | 127.9121 | day
| 81 | NRC-24 | NIRCam Dither-Pattern Verification | 129.1775 | day | 4.73 | hr | 129.3746 | day
| 81 | NRC-24 | NIRCam Dither-Pattern Verification - Ground Analysis | 129.3746 | day | 48 | hr | 131.3746 | day
| 71.13 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 129.9121 | day | 2.13 | hr | 130.0008 | day
| 709.1 | NRC-30.1 | NIRCam Target Acquisition for Coronagraphy (Part 1) | 130.0842 | day | 11.5 | hr | 130.5633 | day
| 376 | NIS-13 | NIRISS Coordinate System Update | 130.6608 | day | 2.31 | hr | 130.7571 | day
| 376 | NIS-13 | NIRISS Coordinate System Update Ground Analysis | 130.7571 | day | 72 | hr | 133.7571 | day
| 819.2 | THS-02 | Wavefront Maintenance | 131.0858 | day | 2.5 | hr | 131.19 | day
| 819.3 | THS-02 | Observatory Pointing Stability (NIRCam/NIRISS) | 131.2733 | day | 3 | hr | 131.3983 | day
| 819.4 | THS-02 | NIRCam IEC Cyclic Drifts Measurement | 131.4817 | day | 2 | hr | 131.565 | day
| 819.5 | THS-02 | NIRCam Internal Phase Retrieval -Hot | 131.6483 | day | 1 | hr | 131.69 | day
| 819.6 | THS-02 | NIRCam Multi-Field + LOS Monitor | 131.7733 | day | 12 | hr | 132.2733 | day
| 819.7 | THS-02 | Hot attidude ground analysis | 132.2733 | day | 6 | hr | 132.5233 | day
| 105 | NRC-19 | NIRCam Subarray-Mode Commissioning | 132.3246 | day | 3 | hr | 132.4496 | day
| 105 | NRC-19 | NIRCam Subarray-Mode Commissioning - Ground Analysis | 132.4496 | day | 48 | hr | 134.4496 | day
| 811.1 |  | Cold Attitude CAM | 132.5233 | day | 2 | hr | 132.6067 | day
| MILESTONE |  | Slew & Remain at COLD ATTITUDE (-40 +/- 5 deg pitch) | 132.6067 | day | 336 | hr | 146.6067 | day
| 811.1 | THS-01 | Frill/PMSA/OTE Thermal Distortion PM8 only + Pointing Stability | 132.69 | day | 3 | hr | 132.815 | day
| 811.2 | THS-01 | Frill/PMSA/OTE Thermal Distortion + Pointing Stability | 132.8983 | day | 21 | hr | 133.7733 | day
| 811.3.1 | THS-01 | NIRCam Multi-Field + LOS Monitor | 133.8567 | day | 12 | hr | 134.3567 | day
| 810 |  | SC Bus HDE TCL Characterization | 134.44 | day | 4 | hr | 134.6067 | day
| SEP2 |  | NIRCam Time Series Ground Analysis | 134.4496 | day | 48 | hr | 136.4496 | day
| 811.4.01 | THS-01 | NIRCam Single-Field + LOS Monitor | 134.69 | day | 1.4 | hr | 134.7483 | day
| 812.2 | MIR-73.2 | MIRI Sky background variation with telescope pointing (part 2) | 134.8317 | day | 4.5 | hr | 135.0192 | day
| 811.4.02 | THS-01 | NIRCam Single-Field + LOS Monitor | 135.2483 | day | 1.4 | hr | 135.3067 | day
| 811.4.03 | THS-01 | NIRCam Single-Field + LOS Monitor | 135.8067 | day | 1.4 | hr | 135.865 | day
| 811.4.04 | THS-01 | NIRCam Single-Field + LOS Monitor | 136.365 | day | 1.4 | hr | 136.4233 | day
| MILESTONE |  | NIRCam Grism Timeseries & Photometric Time Series Enable Decision Point | 136.4496 | day | 0.001 | hr | 136.4496 | day
| SEP 3 |  | NIRCam Wide Field Slitless Spectroscopy (WFSS) Ground Analysis | 136.4496 | day | 48 | hr | 138.4496 | day
| 702 | NIS-18 | NIRISS GR700XD Wavelength Calibration | 136.5067 | day | 3 | hr | 136.6317 | day
| 811.4.05 | THS-01 | NIRCam Single-Field + LOS Monitor | 136.9233 | day | 1.4 | hr | 136.9817 | day
| 120.1 | NRC-10.1 | NIRCam External Flats (1 of 5 visits) | 137.065 | day | 11 | hr | 137.5233 | day
| 811.4.06 | THS-01 | NIRCam Single-Field + LOS Monitor | 137.5817 | day | 1.4 | hr | 137.64 | day
| 120.2 | NRC-10.2 | NIRCam External Flats (2 of 5 visits) | 137.7233 | day | 11 | hr | 138.1817 | day
| 811.4.07 | THS-01 | NIRCam Single-Field + LOS Monitor | 138.24 | day | 1.4 | hr | 138.2983 | day
| 706 | NIS-22 | NIRISS PSF Characterization | 138.3817 | day | 4.7 | hr | 138.5775 | day
| MILESTONE |  | NIRCam Wide Field Slitless Spectroscopy (WFSS) Science Enable Decision Point | 138.4496 | day | 0.001 | hr | 138.4496 | day
| 811.4.08 | THS-01 | NIRCam Single-Field + LOS Monitor | 138.7983 | day | 1.4 | hr | 138.8567 | day
| 811.4.09 | THS-01 | NIRCam Single-Field + LOS Monitor | 139.3567 | day | 1.4 | hr | 139.415 | day
| 811.3.2 | THS-01 | NIRCam Multi-Field + LOS Monitor | 139.915 | day | 12 | hr | 140.415 | day
| 90.1 | NRC-17.1 | NIRCam PSF Wings, Glints, and Ghosts (1 of 2 visits) | 140.4983 | day | 15 | hr | 141.1233 | day
| 811.4.10 | THS-01 | NIRCam Single-Field + LOS Monitor | 141.415 | day | 1.4 | hr | 141.4733 | day
| 90.2 | NRC-17.2 | NIRCam PSF Wings, Glints, and Ghosts (2 of 2 visits) | 141.5567 | day | 5 | hr | 141.765 | day
| 74.5 | MIR-05 | MIRI Detector Anneals (to support MIR-51) | 141.8483 | day | 0.5 | hr | 141.8692 | day
| 141 | MIR-51 | MIRI Locations of Centers of Coronagraphs | 141.8692 | day | 2.5 | hr | 141.9733 | day
| 141 | MIR-51 | MIRI Locations of Centers of Coronagraphs - Ground Analysis | 141.9733 | day | 48 | hr | 143.9733 | day
| 120.3 | NRC-10.3 | NIRCam External Flats (3 of 5 visits) | 142.0567 | day | 11 | hr | 142.515 | day
| 811.4.11 | THS-01 | NIRCam Single-Field + LOS Monitor | 142.5233 | day | 1.4 | hr | 142.5817 | day
| 120.4 | NRC-10.4 | NIRCam External Flats (4 of 5 visits) | 142.665 | day | 11 | hr | 143.1233 | day
| 811.4.12 | THS-01 | NIRCam Single-Field + LOS Monitor | 143.6117 | day | 1.4 | hr | 143.67 | day
| 120.5 | NRC-10.5 | NIRCam External Flats (5 of 5 visits) | 143.7533 | day | 11 | hr | 144.2117 | day
| 705 | NIS-21 | NIRISS Stray Light Contamination | 144.295 | day | 4.9 | hr | 144.4992 | day
| 811.4.13 | THS-01 | NIRCam Single-Field + LOS Monitor | 144.77 | day | 1.4 | hr | 144.8283 | day
| 811.5 | THS-01 | NIRCam Internal Phase Retrieval -Cold | 145.9817 | day | 1 | hr | 146.0233 | day
| 811.3.3 | THS-01 | NIRCam Multi-Field + LOS Monitor | 146.1067 | day | 12 | hr | 146.6067 | day
| 811.6 |  | Cold Attitude Ground Analysis | 146.6067 | day | 6 | hr | 146.8567 | day
| 819.8 |  | Hot Attitude CAM | 146.8567 | day | 2 | hr | 146.94 | day
| MILESTONE |  | Slew and Remain at HOT Attitude (0 +/- 5 deg pitch) | 146.94 | day | 3 | hr | 147.065 | day
| 819.8 | THS-02 | Observatory Pointing Stability (NIRCam/NIRISS) | 146.94 | day | 3 | hr | 147.065 | day
| 819.8 |  | Observatory Pointing Stability ground analysis | 147.065 | day | 8 | hr | 147.3983 | day
| MILESTONE |  | Thermal Slew Test Complete | 147.065 | day | 0 | hr | 147.065 | day
| 862.6 |  | Stationkeeping maneuver | 147.1483 | day | 3.33 | hr | 147.2871 | day
| 806 |  | Solar Array Data Gathering & GPD at Hot Attitude | 147.1483 | day | 0.5 | hr | 147.1692 | day
| 83.1 |  | WF Maintenance (every 14 days) | 147.3704 | day | 2.5 | hr | 147.4746 | day
| 124.1 | NRC-29.1 | NIRCam Photometric Zero-Points and Stability | 147.5579 | day | 13 | hr | 148.0996 | day
| 754 | STL-02 | Stray Light Correlation (includes slew to 5 attitudes) | 148.1829 | day | 24.7 | hr | 149.2121 | day
| SEP1 |  | NIRCam Imaging Ground Analysis | 149.2121 | day | 120 | hr | 154.2121 | day
| 707.1 | NIS-20.1 | NIRISS Photometric Zero Points and Stability (Part 1) | 149.2954 | day | 7.6 | hr | 149.6121 | day
| 707.1 | NIS-20.1 | NIRISS Photometric Zero Points and Stability - Ground Analysis | 149.6121 | day | 336 | hr | 163.6121 | day
| SEP 6 |  | NIRISS Imaging Ground Analysis | 149.6121 | day | 120 | hr | 154.6121 | day
| 71.14 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 149.6846 | day | 2.13 | hr | 149.7733 | day
| 709.2 | NRC-30.2 | NIRCam Target Acquisition for Coronagraphy (Part 2) | 149.8567 | day | 7 | hr | 150.1483 | day
| 800 | FGS-05 | FGS - Fine Steering Mirror Offsets | 150.2317 | day | 1.3 | hr | 150.2858 | day
| 74.6 | MIR-05 | MIRI Detector Anneals (to support MIR-78) | 150.3692 | day | 0.5 | hr | 150.39 | day
| 882 | MIR-78 | MIRI Coronagraphic Target Acquisition | 150.39 | day | 11.5 | hr | 150.8692 | day
| 882 | MIR-78 | MIRI Coronagraphic Target Acquisition - Ground Analysis | 150.8692 | day | 48 | hr | 152.8692 | day
| 703 | NIS-19 | NIRISS Non-Redundant Mask (NRM) Performance | 150.9525 | day | 7.9 | hr | 151.2817 | day
| 703 | NIS-19 | NIRISS Non-Redundant Mask (NRM) Performance Ground Analysis | 151.2817 | day | 72 | hr | 154.2817 | day
| 701 | NIS-17 | NIRISS GR700XD Flux Calibration | 151.365 | day | 7.75 | hr | 151.6879 | day
| 701 | NIS-17 | NIRISS GR700XD Flux Calibration Ground Analysis | 151.6879 | day | 48 | hr | 153.6879 | day
| 71.15 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 151.7733 | day | 2.13 | hr | 151.8621 | day
| 699 | NIS-15 | NIRISS GR150C/R Flux and Trace Calibration | 151.9454 | day | 8.67 | hr | 152.3067 | day
| 699 | NIS-15 | NIRISS GR150C/R Flux and Trace Calibration - Ground Analysis | 152.3067 | day | 24 | hr | 153.3067 | day
| 114 | MIR-13 | MIRI MRS/LRS Target Acquisition | 152.39 | day | 7.05 | hr | 152.6838 | day
| 145 | MIR-52 | MIRI Detector Latent Image Characterization | 152.7671 | day | 3.42 | hr | 152.9096 | day
| 74.7 | MIR-05 | MIRI Detector Anneals (to support MIR-72) | 152.9929 | day | 2.4 | hr | 153.0929 | day
| 813 | MIR-72 | MIRI Imager Pixel Flat | 153.0929 | day | 18.7 | hr | 153.8721 | day
| 71.16 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 153.9121 | day | 2.13 | hr | 154.0008 | day
| 227 | MIR-53 | MIRI External Flat Field - Imager | 154.0842 | day | 16.1 | hr | 154.755 | day
| MILESTONE |  | NIRCam Imaging Science Enable Decision Point | 154.2121 | day | 0.001 | hr | 154.2121 | day
| MILESTONE |  | NIRISS - Imaging Science Enabled Decision Point | 154.6121 | day | 0.001 | hr | 154.6121 | day
| 89 | MIR-12 | MIRI Imager PSF Characterization | 154.8383 | day | 10.7 | hr | 155.2842 | day
| 119 | MIR-16 | MIRI Imager and LRS Glints and Scattered Light | 155.3675 | day | 1.6 | hr | 155.4342 | day
| 74.8 | MIR-05 | MIRI Detector Anneals (post MIR-16) | 155.4342 | day | 0.45 | hr | 155.4529 | day
| ERO-1.1 |  | ERO 1 - NRC | 155.4529 | day | 3.3 | hr | 155.5904 | day
| ERO-2.1 |  | ERO 2 - NRC | 155.5904 | day | 3.7 | hr | 155.7446 | day
| ERO-3.1 |  | ERO 3 - NRC | 155.7446 | day | 6.7 | hr | 156.0238 | day
| ERO-4.1 |  | ERO 4 - NRC | 156.0238 | day | 3.4 | hr | 156.1654 | day
| ERO-5.1 |  | ERO 5 - NRC | 156.1654 | day | 3.3 | hr | 156.3029 | day
| MILESTONE |  | NIRISS AMI Science Enable Decision Point | 156.2817 | day | 0.001 | hr | 156.2817 | day
| ERO-6.1 |  | ERO 6 - NRC | 156.3029 | day | 3.8 | hr | 156.4613 | day
| 71.17 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 156.5508 | day | 2.13 | hr | 156.6396 | day
| 116 | MIR-15 | MIRI Spectral Resolution and Dispersion Relation | 156.7229 | day | 11 | hr | 157.1813 | day
| 883 | MIR-76 | MIRI LRS Spectral Resolution and Dispersion Ratio | 157.2646 | day | 2.65 | hr | 157.375 | day
| 88.1 | MIR-11.1 | MIRI Imager Photometric Zero Points and Stability (Part 1) | 157.4583 | day | 11.7 | hr | 157.9458 | day
| SEP7 |  | MIRI Imager Ground Analysis | 157.9458 | day | 120 | hr | 162.9458 | day
| 144 | MIR-18 | MIRI LRS Slit Transmission and Losses | 158.0292 | day | 1.58 | hr | 158.095 | day
| 910 | NIS-34 | Sensitivity & Stability for Transiting Exoplanet Observations | 158.1783 | day | 6.1 | hr | 158.4325 | day
| SEP 4 |  | NIRISS SOSS Ground Analysis | 158.4325 | day | 120 | hr | 163.4325 | day
| 71.18 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 158.5096 | day | 2.13 | hr | 158.5983 | day
| 127 | MIR-50 | MIRI Coronagraphic Scattered Light & Contrast Ratios | 158.6817 | day | 28.55 | hr | 159.8713 | day
| 167 | MIR-63 | MIRI MRS PSF Characterization and Spatial Resolution | 159.9546 | day | 9.68 | hr | 160.3579 | day
| 770 | MIR-74 | MIRI LRS PSF Characterization | 160.4413 | day | 3.87 | hr | 160.6025 | day
| 217 | MIR-58 | MIRI Coronagraph PSF Characterization | 160.6858 | day | 8.63 | hr | 161.0454 | day
| SEP10 |  | MIRI Coronagraphy Ground Analysis | 161.0454 | day | 120 | hr | 166.0454 | day
| 74.9 | MIR-05 | MIRI Detector Anneals (to support MIR-61) | 161.1288 | day | 0.45 | hr | 161.1475 | day
| 165 | MIR-61 | MIRI External Flat Field - MRS | 161.1475 | day | 5.63 | hr | 161.3821 | day
| 83.2 |  | WF Maintenace (every 14 days post thermal slew) | 161.4746 | day | 2.5 | hr | 161.5788 | day
| 216 | MIR-55 | MIRI External Flat Field - Low Resolution Spectrometer | 161.6621 | day | 8.4 | hr | 162.0121 | day
| 769 | MIR-75 | MIRI LRS Extended Source Flat Field | 162.0954 | day | 3.86 | hr | 162.2563 | day
| 74.10 | MIR-05 | MIRI Detector Anneals (to support MIR-56) | 162.3396 | day | 3.1 | hr | 162.4688 | day
| 218 | MIR-56 | MIRI External Flat Field - Coronagraphs | 162.4688 | day | 10.16 | hr | 162.8921 | day
| MILESTONE |  | MIRI Imager Science Enabled Decision Point | 162.9458 | day | 0.001 | hr | 162.9459 | day
| 168.1 | MIR-64.1 | MIRI MRS Photometric Sensitivity and Stability (Part 1) | 162.9754 | day | 9.3 | hr | 163.3629 | day
| SEP8 |  | MIRI MRS Ground Analysis | 163.3629 | day | 120 | hr | 168.3629 | day
| MILESTONE |  | NIRISS SOSS Science Enabled Decision Point | 163.4325 | day | 0.001 | hr | 163.4325 | day
| 214 | MIR-17 | MIRI LRS Photometric Sensitivity and Stability | 163.4463 | day | 3.41 | hr | 163.5883 | day
| SEP9 |  | MIRI LRS Ground Analysis | 163.5883 | day | 120 | hr | 168.5883 | day
| 71.19 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 163.6088 | day | 2.13 | hr | 163.6975 | day
| ERO-7 |  | ERO 7 - NIS | 163.6975 | day | 15.4 | hr | 164.3392 | day
| ERO-9 |  | ERO 9 - NIS | 164.3392 | day | 12.5 | hr | 164.86 | day
| 164.1 | FGS-15.1 | FGS Moving Target Test (Observation 1 of 3) | 164.9433 | day | 1.5 | hr | 165.0058 | day
| 164.1 | FGS-15.1 | FGS Moving Target Test (Observation 1 of 3) Ground Analysis | 165.0058 | day | 36 | hr | 166.5058 | day
| 225.1 | NRS-17.1 | NIRSpec Wide Aperture Target Acquisition (WATA) Verification | 165.0892 | day | 4.5 | hr | 165.2767 | day
| 225.1 | NRS-17.1 | NIRSpec Wide Aperture Target Acquisition (WATA) Verification - Analysis | 165.2767 | day | 24 | hr | 166.2767 | day
| 918 | FGS-20 | Testing JWST Fine Guilding in Crowded Fields | 165.36 | day | 2.83 | hr | 165.4779 | day
| 700 | NIS-16 | NIRISS GR150C/R Wavelength Calibration | 165.5613 | day | 6.13 | hr | 165.8167 | day
| 700 | NIS-16 | NIRISS GR150C/R Wavelength Calibration- Ground Analysis | 165.8167 | day | 48 | hr | 167.8167 | day
| 71.20 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 165.8475 | day | 2.13 | hr | 165.9363 | day
| MILESTONE |  | MIRI Coronagraphy Science Enabled Decision Point | 166.0454 | day | 0.001 | hr | 166.0455 | day
| 225.2 | NRS-17.2 | NIRSpec Wide Aperture Target Acquisition (WATA) Verification | 166.2767 | day | 1.7 | hr | 166.3475 | day
| 110 | NRS-16 | NIRSpec Standard Target Acquisition Verification | 166.4308 | day | 4 | hr | 166.5975 | day
| 110 | NRS-16 | NIRSpec Standard Target Acquisition Verification - Ground Analysis | 166.5975 | day | 48 | hr | 168.5975 | day
| ERO-1.1 |  | ERO 1 - MIR | 166.5975 | day | 3.8 | hr | 166.7558 | day
| ERO-2.1 |  | ERO 2 - MIR | 166.7558 | day | 6.9 | hr | 167.0433 | day
| ERO-3.1 |  | ERO 3 - MIR | 167.0433 | day | 10.4 | hr | 167.4767 | day
| ERO-4.1 |  | ERO 4 - MIR | 167.4767 | day | 6.7 | hr | 167.7558 | day
| ERO-5.1 |  | ERO 5 - MIR | 167.7558 | day | 3.8 | hr | 167.9142 | day
| SEP5 |  | NIRISS WFSS Ground Analysis | 167.8167 | day | 120 | hr | 172.8167 | day
| ERO-6.2 |  | ERO 6 - MIR | 167.9142 | day | 7.8 | hr | 168.2392 | day
| 71.21 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 168.2863 | day | 2.13 | hr | 168.375 | day
| MILESTONE |  | MIRI MRS Science Enabled Decision Point | 168.3629 | day | 0.001 | hr | 168.363 | day
| 164.2 | FGS-15.2 | FGS Moving target Test (Observation 2 of 3) | 168.375 | day | 2.65 | hr | 168.4854 | day
| 164.3 | FGS-15.3 | FGS Moving target Test (Observation 3 of 3) | 168.5688 | day | 1.5 | hr | 168.6313 | day
| MILESTONE |  | MIRI LRS Science Enabled Decision Point | 168.5883 | day | 0.001 | hr | 168.5884 | day
| MILESTONE |  | Comet and Asteroid Moving Target Science Enable Decision Point | 168.6313 | day | 0.001 | hr | 168.6313 | day
| 124.2 | NRC-29.2 | NIRCam Photometric Zero-Points and Stability | 168.7146 | day | 2.5 | hr | 168.8188 | day
| 88.2 | MIR-11.2 | MIRI Imager Photometric Zero Points and Stability | 168.9021 | day | 3.64 | hr | 169.0538 | day
| 907 | NRC-31 | NIRCam Coronagraphic Suppression | 169.1371 | day | 17 | hr | 169.8454 | day
| 774.1 | FGS-17.1 | FGS Giant Planet Scattered Light (NIRCam) | 169.9288 | day | 1.4 | hr | 169.9871 | day
| 774.2 | FGS-17.2 | FGS Giant Planet Scattered Light (NIRISS) | 169.9871 | day | 7.76 | hr | 170.3104 | day
| 774.3 | FGS-17.3 | FGS Giant Planet Scattered Light (MIRI) | 170.3104 | day | 2.8 | hr | 170.4271 | day
| 774.4 | FGS-17.4 | FGS Giant Planet Scattered Light (NIRSpec) | 170.4271 | day | 2.35 | hr | 170.525 | day
| MILESTONE |  | Planet and Planetary Satellite Science Enable Decision Point | 170.525 | day | 0.001 | hr | 170.525 | day
| 71.22 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 170.575 | day | 2.13 | hr | 170.6638 | day
| 142 | NRS-26 | NIRSpec MSA external wavelength calibration | 170.7375 | day | 15.05 | hr | 171.3646 | day
| ERO-14 |  | ERO 14 - MIR | 171.3646 | day | 3 | hr | 171.4896 | day
| ERO-15 |  | ERO 15 - MIR | 171.4896 | day | 4 | hr | 171.6563 | day
| 71.23 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 171.7038 | day | 2.13 | hr | 171.7925 | day
| 150 | NRS-32 | NIRSpec On-Sky Throughput Measurements | 171.8758 | day | 44.1 | hr | 173.7133 | day
| MILESTONE |  | NIRCam Basic Coronagraphy Science Enable Decision Point | 172.1371 | day | 0.001 | hr | 172.1371 | day
| MILESTONE |  | NIRISS WFSS Science Enable Decision Point | 172.8167 | day | 0.001 | hr | 172.8167 | day
| 772 | NRS-42 | NIRSpec Slit Loss Characterization for MSA Shutters | 173.7967 | day | 10.3 | hr | 174.2258 | day
| SEP11 |  | NIRSpec Science Ground Analysis | 174.2258 | day | 120 | hr | 179.2258 | day
| 71.24 | OTE-26 | WFSC Routine/CC Jitter Maintenance | 174.2925 | day | 2.13 | hr | 174.3813 | day
| 74.11 | MIR-05 | MIRI Detector Anneals (to support MIR-77) | 174.4646 | day | 3.1 | hr | 174.5938 | day
| 873 | MIR-77 | MIRI Bright Source Sensitivity | 174.5938 | day | 3.15 | hr | 174.725 | day
| 226 | NRS-25 | NIRSpec Ghosts, Glints & Scattered Light Check | 174.8083 | day | 3 | hr | 174.9333 | day
| 168.2 | MIR-64.2 | MIRI MRS Photometric Sensitivity and Stability (Part 2) | 175.0029 | day | 2.07 | hr | 175.0892 | day
| 707.2 | NIS-20.2 | NIRISS Photometric Zero Points and Stability (Part 2) | 175.1621 | day | 7.6 | hr | 175.4788 | day
| 919 | FGS-21 | NIRSpec Moving Target Test | 175.5621 | day | 2.8 | hr | 175.6788 | day
| 920 | MIR-90 | MIRI Moving-Target Tracking Test | 175.7621 | day | 1.3 | hr | 175.8163 | day
| MILESTONE |  | Observatory Commissioning Complete | 175.8163 | day | 0 | hr | 175.8163 | day
| ERO-12 |  | ERO 12 - NIS | 175.8163 | day | 4.5 | hr | 176.0038 | day
| ERO-13 |  | ERO 13 - NIS | 176.0038 | day | 5 | hr | 176.2121 | day
| MILESTONE |  | NIRSpec Single Object Spectroscopy Science Enable Decision Point | 179.2258 | day | 0.001 | hr | 179.2259 | day
| MILESTONE |  | NIRSpec Bright Object Time Series Spectroscopy Science Enable Decision Point | 179.2258 | day | 0.001 | hr | 179.2259 | day
| MILESTONE |  | NIRSpec Integral-Field Spectroscopy Science Enable Decision Point | 179.2258 | day | 0.001 | hr | 179.2259 | day
| MILESTONE |  | NIRSpec Multi-Object Spectroscopy Enabled Decision Point | 179.2258 | day | 0.001 | hr | 179.2259 | day
| ERO-8 |  | ERO 8 - NRS | 179.2259 | day | 4.3 | hr | 179.405 | day
| ERO-10 |  | ERO 10 - NRS | 179.405 | day | 4.1 | hr | 179.5759 | day
| ERO-11 |  | ERO 11 - NRS | 179.5759 | day | 2.3 | hr | 179.6717 | day